Homes England Multidisciplinary Framework

(Procurement Number 2018/S127-289621)

Further Competition Invitation to Tender (Stage 3 Over FTS Threshold)

Langley SUE – Planning, Design and Technical Disposal Support/ Quality Assurance

Issue Date: 1st June 2022

ProContract Identification Number: DN596695

Table of Contents

Introduction	4

Part 1 - Commission Requirements	5

1.	Commission Background	5

1.1	Strategic Context	5

2.1	Langley SUE	6

2.1.1	Site/ background	6

2.1.2	Planning Status	8

2.1.3	Homes England Strategic Vision	10

2.2	Development and Infrastructure Delivery	11

2.2.1	Site wide delivery and infrastructure	11

2.2.3	Delivery of Homes England land	13

Draft phasing plan	13

3	The Services	13

4	Indicative Programme	17

5.	Management	18

5.1	Homes England Personnel	18

5.2	Other personnel	19

5.3	Meeting Requirements	19

5.4	Invoicing	20

6.	Other Requirements	20

6.1	Termination	20

6.2	Conflict of Interest	20

6.3	Confidentiality	20

6.4	Future changes to scope of works	21

Part 2 - Instructions for Submitting a Response	22

1	General	22

2	Quality	23

3	Pricing	23

4	Evaluation	24

5	Documents to be Returned	25

6	Procurement Timetable	24

7	Evaluation Criteria	26

Part 3 Response Form	31

# Introduction

The purpose of this Further Competition Invitation to Tender (ITT) is to award the call-off contract for the above commission.

We ask you to respond to the questions detailed in Part 2, Section 6 (Evaluation Criteria) using the Response Form and to return the Response Form and Resource and Pricing Schedule in Part 3 with your tender.

This Further Competition ITT is divided into 3 parts:

Part 1 – Commission Requirement

- Details the commission requirements.

- Details additional terms and conditions for the Further Competition.  The successful Supplier will be subject to both the terms and conditions of this Further Competition and the Framework Contract.  Unless otherwise defined in these instructions, terms used shall have the meaning given to them in the Framework Contract.

Part 2 – Instructions for Submitting a Response

- Contains important information and instructions on preparing and submitting a tender response.  Please read these instructions carefully prior to submitting your tender response.

- Outlines the evaluation criteria which will be used for assessment.  It is important that Suppliers familiarise themselves with the criteria and ensure they are considered when compiling their tender response.

Part 3 – Standard Forms

- Contains the standard forms required to be completed and returned by the Supplier when submitting a tender response.

# Part 1 - Commission Requirements

# Commission Background

# Strategic Context

    - Homes England set out a five-year strategic plan in 2018, which can be accessed using the link below. A new strategic plan is anticipated in 2022.

https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/752686/Homes_England_Strategic_Plan_AW_REV_150dpi_REV.pdf

    - In line with our organisational strategic objectives, we have a mandate to:

- Provide expert support for priority locations, helping to create and deliver more ambitious plans to get more homes built.

- Promote better design and higher quality places.

- Understand the need and opportunity for investment in land, infrastructure to unlock the market and support affordability of housing.

    - As part of the Agency’s 5-year plan, a number of significant acquisitions of large-scale stalled sites have been made, and the acquisition of circa 94.68 ha (234 acres) of land capable of delivering over 2,200 homes at Langley Sustainable Urban Extension (SUE) represents one of these recent acquisitions (2021).

    - As a Government Agency, Homes England will be a key agent for the delivery of Government Objectives currently being formulated by Central Government within the Levelling Up Bill. The Consultant team will be expected to be aware of, and mindful of, the provisions within the Bill (and implications for the project) as it progresses through Parliament.

    - This commission is to appoint a Multi-Disciplinary (MD) Consultant to deliver a cluster of services, to support Homes England in the delivery of its vision and landholdings within the Langley Strategic Urban Extension in Birmingham. Also, to support the wider delivery objectives of the SUE and to enable a collaborative approach to working with Consortium Partners, Birmingham City Council and other key stakeholders whilst protecting Homes England’s interests.

# Homes England’s Strategic View for Langley

    - Homes England’s Strategic Vision is for the Langley SUE to not only deliver up to 6,000 new homes, but to establish a new sustainable community, including schools and community facilities, and set a national benchmark for high quality development at this scale, bringing benefits not only to new residents, but to the wider area of Walmley, Sutton Coldfield and beyond.

- Homes England will look to achieve this vision for an Exemplar development by: delivering the right infrastructure at the right time, that is in the right place, is safe, accessible, legible, beautiful and fit for the future, that underpins the creation of great places;

- Delivering a series of serviced parcels for development on its own land by high quality developers including SMEs as well as larger and well-established national / regional housebuilders;

- Creating the opportunity on land Homes England owns for smaller, appropriately serviced plots for smaller developers, custom and self-builds and new market entrants;

- Ensuring that our approach to disposing of parcels of land ensures the delivery of a successful, sustainable and commercially facing range of different tenures, traditional and non-standard products to create a varied and long-lasting community and sense of place;

- Working with the Consortium to create a locally distinctive and characterful place, that builds on and connects strongly with the local community;

- Delivering a commercially successful series of retail, leisure, education and non-residential spaces that create a truly thriving and sustainable community;

- Creating sustainable and ambitious long-term partnerships and stewardship arrangements that incorporate and become exemplars in co-design and community management models, delivering a community-based vehicle to take stewardship of key assets in perpetuity;

- Incorporating and promoting innovation and aspiration in new technologies and approaches to sustainable construction, design and infrastructure to ensure the development built will be fit for future generations; and

- Creating a well-connected site which encourages sustainable methods of movement and integration with the existing local community.

Key objectives of this Commission are:

- To support the Homes England Project Team to deliver the Vision of an exemplar and commercially deliverable scheme;

- To ensure that Homes England understands and manages its risk exposure as part of the Masterplan development, to include the infrastructure works programme, working with Birmingham City Council and the other Consortium Members;

- To ensure that the development and disposal process for Homes England, as part of the Consortium, optimises the opportunities at parcel level; and

- To champion and protect Homes England’s position as part of the wider Consortium, and to ensure our interests and opportunities to meet the Agency Vision for the site are maximised.

# Langley SUE

# Site/ background

      - The Langley Sustainable Urban Extension (SUE) is located adjacent to Sutton Coldfield and is a major residential development, covering approximately 264 hectares (652 acres).  Situated 2 miles east of Sutton Coldfield Town Centre and 8 miles northeast of Birmingham City Centre, it’s in close proximity to the A38, M42 and M6 Toll, having excellent connectivity to the motorway network.

      - The SUE will be primarily delivered by four major landowners and developers; Homes England, Taylor Wimpey, Vistry and Rubery Owen, acting in partnership through a Consortium Collaboration Agreement, which will set out the terms and structure for joint delivery of the project.

      - Homes England’s role in delivering this vision is two-fold. Firstly, the Agency has acquired 36% of the land within the Langley SUE area. It will therefore have a direct role in delivering homes and infrastructure within the land it owns. Homes England will deliver circa 2,200 homes on its landholdings, with our aim that at least 35% of these are genuinely affordable. Secondly, as part of the Consortium, Homes England will collaborate with the other members to develop the respective planning application submissions, design codes and shared delivery model for major infrastructure that will underpin the delivery of the overall vision for the SUE.

      - The Langley SUE was released from the green belt and allocated in the Birmingham Development Plan in 2017.  The Langley SUE Supplementary Planning Document (SPD) was published in 2019, the main focus being the delivery of a comprehensive, sustainable and high-quality development.  The site allocation is illustrated in the plan below, taken from the Langley SUE SPD:

Figure 1: Langley SUE allocation boundary

      - The SPD includes a requirement for a comprehensive site-wide phasing and infrastructure plan, which was proving difficult due to the involvement of multiple landowners and promoters.  Homes England acquired circa 94.68 hectares (234 acres) in 2021, circa 36% of the wider site, and has subsequently worked closely with the landowners/ promoters in the negotiation of a Pre-Planning Collaboration Agreement that sets out the intention for the terms and structure for joint delivery of the project.  The Consortium members include Homes England, Taylor Wimpey, Vistry Homes, William Davis and Rubery Owen; collective ownership totals approximately 90% of the SUE designation.  The ownership/ promotion boundaries of the site are identified on the plan below:

Figure 2: Langley SUE ownership plan

# Planning Status

      - Since the adoption of the Birmingham Development Plan (BDP, 2017), the Langley Consortium has worked collaboratively to produce a site wide masterplan that sets out a deliverable vision for the site. The Consortium subsequently submitted an outline planning application in December 2021 (Planning Application Number 2021/10567/PA), which is currently being determined. In accordance with the SPD, the outline planning application is for up to 6000dwellings and will include:

- Affordable housing.

- Mixed-use centre (District Centre).

- Two local hubs (Community Hubs).

- Education provision (early years, 3no. primary schools, 1no. secondary school and sixth form);

- Community facilities (including health facilities, extensive public open space, sports and play facilities).

- Two new access points to the A38.

- Highway improvement and mitigation.

- Public transport provision.

- A network of walking and cycling routes.

      - Following submission of the outline planning application, the Consortium’s consultant team is now working up a full strategic infrastructure application, which is anticipated to be submitted in September/ October 2021. This will cover strategic infrastructure works, including the internal road network, strategic green and blue infrastructure, a site wide drainage scheme and utilities upgrades/diversions. The application will confirm the location of key infrastructure works, which will determine the extent of the development parcels. Strategic design codes are currently being prepared by Savills, which will inform infrastructure design and delivery. They will also set out key design principles for the character areas, as identified in the Design and Access Statement. These codes will ensure a consistent approach to design quality regardless of landownership, which is key as reserved matters applications will be progressed by various developers within the Consortium or those selected through the Agency’s disposal process.

Figure 3: Masterplan showing the extent of Homes England ownership

# Homes England Strategic Vision

      - The legal structure for delivery of the overall scheme is currently being agreed with the Consortium Members and will consist of a Collaboration Agreement that sets out in detail the arrangements for delivering the strategic infrastructure across the SUE and specific land parcels.

# Consultant Appointments

      - The MD Consultant will be required to work closely with the Consortium and Homes England Consultant teams to ensure that Homes England objectives are promoted in a consistent manner across all workstreams.  The Consortium has appointed a consultant team to advise on site wide delivery, including preparation of the outline planning application (submitted), phasing, site wide infrastructure and preparation of Design Codes.  The Consortium technical team includes the following appointments.

- Ellipsis: Project Manager, to coordinate the development delivery (recently appointed).

- WSP: Engineering and Infrastructure Specialist.

- Savills: Property, Planning and Urban Design Specialist.

- Arcadis: Cost Consultant Specialist.

- Various subconsultants supporting Savills and WSP.A specialist consultant will be appointed in due course to advise on long term stewardship, which is key to successful place making and ensuring the site is effectively managed and maintained when all landowners dispose of their interests.

      - Homes England are looking to make the following additional appointments, which will be subject to different procurement exercises, to act on behalf of the Agency. The appointed MD Consultant will be required to work closely via the workstream leads for each commission with all of the consultants to ensure seamless integration and collaboration:

- Property Consultancy services to support the delivery of the disposal strategy, including viability analysis, valuation and professional property advice.

- Legal advice in respect to disposal contracts and other ad hoc/miscellaneous legal advice as may be necessary.

- The appointment of a Property Agent, to advise on the disposal of Homes England phases via the Agency’s Dynamic Purchasing System (DPS), may be undertaken as a new tendering exercise at the appropriate time.

- Additional specialist advice is likely to be required as the project develops, relating to education and retail provision, as well as town centre development; the scope of which will be determined in due course.

      - It will be necessary to set up a reporting/ exchange of information regime, in order that all strands of work are shared on a cohesive basis.

# Development and Infrastructure Delivery

# Site wide delivery and infrastructure

      - The SUE will be primarily delivered by four major landowners and developers, namely Homes England, Taylor Wimpy, Vistry and Rubery Owen, acting in partnership through a Consortium Collaboration Agreement, which will set out the terms and structure for joint delivery of the project.

      - The Consortium will have responsibility for the delivery of site wide infrastructure works through a contractual arrangement between Consortium members, the format of which is yet to be agreed. This ‘Project Infrastructure Contract’ (PIC) will have responsibility for delivery of the following packages of works:

- Site clearance, remediation and groundworks

- Section 38 and 278 highway works along with relevant adoptions

- Servicing and utilities

- Masterplanning of blue and green infrastructure to support planning requirements

- Drainage, attenuation, waste, pumping and sub stations

- Demolitions of various buildings within the Masterplan, to include the Farm house (and may include the 2x3 bed semi houses on Homes England Land)

- Acoustic barriers

      - A full strategic infrastructure application for the above works is currently being worked up by WSP and associated sub consultants. When submitted to the LPA, this application will be reviewed alongside the illustrative masterplan to ensure seamlessness between the proposals, which will support the delivery of the site. In terms of infrastructure delivery, the MD Consultant will need to take a value engineering approach, advising on where potential cost savings could be made, whilst ensuring a high-quality scheme is delivered/ the vision is maintained and the requirements of statutory consultees are satisfied. This will require a review of the Project Cost Plan, which has been prepared by Arcadis.

      - The Consortium is currently collating all of the key information required to support the full infrastructure application and strategic design codes.

    - Site Constraints and Considerations

      - As an outline application has been submitted, a wide range of reports and supporting technical information is held on the BCC planning portal platform, which outline the general constraints of the site. It will be necessary for the MD Consultant to review this information as part of the task activity, and to effectively respond to this ITT.

      - Other documents are in the process of being prepared, including a comprehensive constraints plan, which will form a critical part of the infrastructure workstream; indicative details surrounding the proposals for the Project Infrastructure Works can be reviewed at Appendix A. Also, a series of preliminary constraints information is contained in Appendix B, providing information on known services and physical constraints as part of the development. This does not include pre-existing services that are to be protected as part of the works contract. A plan is currently being prepared to inform the Consortium of any pre-existing services, in relation to easements, pipes, wires and cables that cut across the Masterplan area (contained within conveyances of land holdings that may serve third parties). This plan information will contribute to a comprehensive composite constraints plan that will form part of the Infrastructure Works Contract. This will be available for the MD Consultant by the time the appointment is made, or shortly thereafter.

      - In terms of Homes England landholdings, capacity testing is underway for Agency parcels to ensure efficient and deliverable plots are created. This piece of work will help to confirm the location of strategic infrastructure, including primary roads. Also, Barton Willmore have previously undertaken a BfHL12 assessment of the outline scheme, and this will need to be revisited as part of the MD scope.

      - Space Syntax have been commissioned to undertake accessibility modelling for the development, to ensure the proposed Masterplan maximises connectivity within the development and beyond. The Langley SUE policy within the adopted BDP refers to the creation of a Green Travel District (GTD), and sustainable modes of travel/ promoting active travel is a key consideration of the overall scheme. The MD Consultant will need to take this into account, and ensure the infrastructure application prioritises sustainable modes, as well as parcel specific design codes (plot passports). The Agency and/or Consortium is liaising directly with Transport for West Midlands (TfWM) on the proposed SPRINT route, which will connect Langley to Birmingham City Centre in the long term and associated public transport matters.

      - There may be other key stakeholders that the Agency may wish to engage with as proposals develop, who will be identified during the course of the commission.

    - Delivery of Homes England Land

      - As landowner, Homes England will also have responsibility for the delivery of infrastructure and development on its own land holdings.

# Draft Phasing Plan

      - The outline planning application contains a broad phasing strategy for both strategic infrastructure and development plot parcels, with a proposed 15 year build out period. As is stands, early phases of development comprise parcels fronting Springfield Road, that do not rely on the delivery of infrastructure works to open access to the ‘internal’ site to begin early delivery of the wider scheme. However, phasing is currently being reviewed by the Consortium as part of the strategic infrastructure design work, taking on board consultee responses from the outline application. A final Phasing and Delivery Plan which fixes plot release timings and confirms capacities will be agreed between Consortium members as part of the Post-Planning Collaboration Agreement currently being prepared. This MD appointment will have an important role in ensuring this phasing plan protects Agency interests and project vision (ie. delivery of its parcels to the market in line with the vision).

      - The proposed District Centre for the development falls within Homes England ownership and this area of land, along with all proposed community land use, will be managed and coordinated as part of the Homes England enabling role. Long Term Stewardship and Placemaking will play a large part in the evolving proposed land uses that form part of the District Centre and Community Hubs; the latter are smaller areas of community and commercial uses. One of the Community Hubs is within Agency ownership, and the other sits with another member of the Consortium. The MD Consultant will be required to advise on the design of the District Centre and smaller Community Hubs; further detail is provided below.  Such design will be to Block Plan stage and will require specialist design around education and health land uses. To include DfE Guidance BB103 and safeguarding requirements for Education, with Health Guidance for any development of health land use as part of the development of the District Centre. Space Syntax as part of their role in assisting Homes England will also carry out a review of the location of the District Centre as part of its commission, working with the specialist Architect appointed to develop the Block Plan design for the District Centre and key movement connections and locations of uses.

# The Services

  - The purpose of this Competition Invitation to Tender (ITT) is to appoint a MD Consultant to provide overarching support to Homes England to deliver the project. More specifically, it will support the Agency, as part of the Consortium in securing the required planning consents for Langley (quality assurance role), and technical support for site disposals, which will include design and Masterplanning input for specific Agency parcels. In terms of the latter, the disposal strategy for the Agency landholdings will be determined in due course, in consultation with the Consortium. This ITT response will need to demonstrate that the proposed MD Consultant Team has strong client relationship skills and collaboration abilities, that are solution focused, and are able to work with multiple interests, objectives and partners.

  - The contract is anticipated to run for an initial period of 3 years, with the option to extend by a further 2 years in increments of 1 year; a total potential contract duration of 5 years, subject to an annual performance review.

  - Homes England will require the appointed consultant to undertake the key services listed below and in the following section on Stages. This is not an exhaustive list, and the supplier is requested to make any recommendations for amendments or additions in their return. Please note, we reserve the right to amend the scope of services to meet the requirements as the project progresses.

  - Suppliers should provide an approach and fee quote for each element of the stages outlined.

PLEASE NOTE: There is a Resource & Pricing Schedule H which needs to be completed as part of the ITT response. This table is to be completed for the purposes of the financial bid and will also be scored for responding to the qualitative elements of the bid including appropriate allocation of resource.

  - The Consortium have a collective responsibility to secure the outline planning consent (currently being determined) and to submit a full strategic infrastructure application, which is currently being progressed. Homes England will support this process as a member of the Consortium, through its commitment to part fund, and will also need to ensure its own development objectives are achieved. Homes England therefore has several key strands of work/ roles as part of this project, including:

- Its participation as a stakeholder and supporting enabler as part of the Consortium, driving forward best practice and the delivery of an ‘exemplar’ scheme.

- The disposal of the District Centre Land, which is anticipated to be via the Agency’s Dynamic Purchasing System (DPS), although there may be an alternative disposal route considered to be appropriate (subject to approvals at that time); and

- The disposal of the Homes England parcels via the DPS process.

- Project governance, business planning, departmental reporting/ monitoring and statutory compliance, including health and safety.

  - Key outputs of the commission include the following, which are expanded upon in more detail below:

- A desk-top, quality assurance review of the work undertaken/ commissioned by the Consortium to date, including specified outline planning documents, as well as any supporting documents to support the full infrastructure application and cost plan.  Matters of concern affecting Homes England will need to be highlighted, outlining risks and gaps, and solutions identified.

- To provide design input the proposed District Centre and Community Hubs. A specialist consultant will need to be identified for this element, given the importance of the District Centre in terms of place making, and the need to incorporate a diverse range of commercial, educational, recreational, arts/ cultural and community uses, delivery strategies (eg parking and servicing), alongside residential development.

- Input into the disposal process for Agency parcels, specifically the preparation of technical packs, supporting the drafting of ITT documentation/ evaluating tender submissions, preparing design guidance/ proving layouts and design review at the Reserved Matters ( RM )stage.

- General planning advisory role, reviewing draft planning conditions, draft S106 and assisting with discharge of conditions where necessary.

Stage 1 – Full pricing schedule for the following tasks; see Appendix D  for additional detail to inform pricing schedule

- Technical output: Review of technical documentation (existing and emerging), including documents that will form part of the full strategic infrastructure application. This will include a gap analysis exercise, to ensure all considerations have been taken into account. Where gaps are identified, the consultant may be required to liaise with Ellipsis on the commissioning of this work, or there may be occasions where Homes England wish to commission the work as part of this instruction.  There are additional documents that have been completed by the Consultants to the Consortium. Those key documents identified below, are currently being reviewed and amended to reflect the evolving design process that is currently taking place.

  - Phasing plan

  - Roads Hierarchy and mitigation works

  - Earthworks Strategy

  - Approach to green/blue/grey infra design

  - Haul Roads/Routes and Construction Management Plan

- Planning and Design output: Strategic Site Wide Design Codes are being prepared by Savills, which will take account of strategic infrastructure and its relationship to the built form and key character areas, as identified in the Design and Access Statement (DAS). These will need to be reviewed by the MD Consultant to ensure they meet the Agency’s vision for the site, as well as planning policy requirements/ City Council expectations.  At the individual parcel level, the MD Consultant will be required to prepare Parcel Codes to guide the detailed design of parcels, which will be delivered by the Agency’s procured developer partners; see Stage 2a below for more detail on Parcel Design Codes and other standards.

- Quality Assurance review of Draft Planning Conditions, Committee Report and S106 obligations and provision of written commentary on acceptability and deliverability.

- Cost planning and value engineering: Monitor consultant fees and costs and undertake regular cost reporting against Business Plan outputs.

- Project management and co-ordination: Umbrella role to ensure all strands sit together and awareness of development delivery, legal matters, risk management, CDM/PD role and statutory compliance matters, communication with Client, input into PR/Communications/Engagement. Preparation and monitoring of the Project Execution Plan.

- Advisory support to the Agency on specialist areas given the need to deliver an exemplar scheme. This could include advising on a Sustainability Strategy (including energy, water and waste provision), Multi-modal Shift and Active Travel, Biodiversity Net Gain and Building with Nature proposals.

- There may be further requirements to engage in workshop sessions with other government departments, such as EA, BEIS and DfE, during the development of the project.

- Development/ compliance monitoring. The MD Consultant will be required to undertake a high level QS monitoring role for the strategic infrastructure that serves Homes England development parcels ie. ensure the appointed contractors construct the strategic infrastructure to the correct specification, location and standards on site. Whilst Ellipsis will perform an overarching development monitoring role for the Consortium, the Agency will require its own consultant QS to perform a monthly check on site, in liaison with Ellipsis and the Contractor, reporting back to the Workstream lead and Project Team on progress and performance

- The Agency wishes to reserve the right to commission specific architectural/urban design input to the proposed District Centre and Community Hubs, working with the Property Consultant and Consortium Consultant Team (ie. Savills Retail Team, who are currently drafting a retail strategy), OR for this role to be undertaken by a Consortium led appointment.  For the purposes of this ITT and tender, a specialist consultant will need to be identified as part of this submission, given the importance of the District Centre in terms of place making, and the need to incorporate a diverse range of commercial and community uses, alongside residential development.     For pricing purposes include a sum of £75,000 and this will be reviewed, and instructions confirmed during the course of this instruction.

Stage 2a – Full pricing schedule for parcel disposal

During the initial 3-year contract period, it’s anticipated there will be one Agency disposal; other Consortium members will be working up schemes for their parcels. Work is on-going to determine phasing, which will identify where development will take place in the short-term; this will be dependent on infrastructure delivery and where there is sufficient infrastructure already in place to enable development (including highways and utilities). Whilst a property consultant will be appointed to lead on the marketing and disposal of the parcel, the MD consultant will need to undertake the following tasks:

- Input into writing DPS Invitation to Tender on technical, planning and design matters.

- Planning and Design – preparation of Proving Layout/ Parcel Code, specific to the phase in question. This will need to accord with the outline consent, including the Strategic Site Wide Design Codes, as well as Birmingham City Council’s local planning policy requirements, including the Langley SPD and Development Management DPD (which requires minimum space standards to be applied). Also, compliance with Building for a Healthy Life (BfHL) is required, alongside principles such as accessibility and inclusion, active lifestyles Secure by Design requirements

- Prepare comprehensive technical pack for disposal, identifying key documentation that will inform developer bids/ submissions. The scope of a typical technical pack is outlined at Appendix E

- Whilst the above scope will be undertaken by the MD Consultant Team, ‘Design Midlands’ will need to be appointed to undertake a pre-assessment of the parcel code and Building for a Healthy Life (BfHL) principles, which reflects the Agency’s current approach to disposals. This will need to be reflected in the ITT response, and a sub consultant arrangement would need to be put in place. The MD Consultant, specifically the identified urban designer/ masterplanner, will need to liaise with the Design Network directly to ensure a joined-up approach to design quality.

- Undertake any additional surveys in relation to Agency land, that will assist with the disposal and form part of the technical pack. Provide an approximate cost for topographical surveys at parcel level.

Stage 2b – Indicative lump sum for disposal work (to be kept under review and agreed at the relevant time in accordance with tendered rates)As part of the marketing process, the MD Urban Designer will need to support the briefing process to bidders (attendance at two developer workshops for up to 5 bidders), outlining the design aspirations for the parcel and how it relates to the wider scheme. The MD technical lead will also need to be involved in the disposal process, and input into clarification responses where necessary. This will follow through when the tenders are submitted, and the relevant technical leads will input into the evaluation, providing a commentary on deliverability, risk and planning/ design considerations. Note that ‘Design Midlands’ will evaluate the BfHL self-assessments submitted by bidders.

- When a preferred bidder is identified, support will be required to draft the Gateway approval paper; allocate 2 days of resource for this. Support will also be required up until the Agency enters into conditional contract with the bidder, when approval to do so is secured; 2 days of resource should be allocated for this. Support developer in refining RM submission/ detailed scheme, to reflect pre application advice (both workshops and written feedback). Also, provide support through RM determination period as needed, ensuring planning conditions are deliverable and reasonable.

Stage 3 – Indicative lump sum to undertake the following tasks (to be kept under review and agreed at the relevant time in accordance with tendered rates); an ability to draw down under the following headings should these be required, or not to draw down if not needed . This stage of the ITT submission will not be scored

- Support the Agency with subsequent disposals, replicating Stages 2a and 2b, which is based on the Agency’s first disposal. Identify an indicative lump sum.

- Option to call down support to review draft infrastructure delivery arrangements and contracts where they relate to technical matters eg. trailing wires, contractual documentation, transfers etc – Assume 5 Consultant days.

- Option to call down support to review/draft necessary Development Strategies that may emerge – Assume 5 Consultant days.

- Support to the Agency in the development of the Long-Term Stewardship approach, Exit Strategy and proposals by the Consortium, in respect of technical/planning and development matters of relevance. Assume 5 Consultant days.

- Light touch overview of Ellipsis managing/monitoring pre-commencement conditions with a specific focus on those of relevance to Agency landholdings and developer partner schemes. Assume 1 Consultant Day month during the delivery stage.

- Support to the Agency in any necessary variations to the OPA/Infrastructure applications as necessary in a quality assurance role. Assume 5 Consultant days.

- Support to the Agency in respect of technical approvals, statutory provider issues, insofar as they relate to the Agency landholdings. Assume 5 Consultant  days.

- Ongoing support to the Agency in respect of phasing and delivery strategies – assume up to 5 Consultant days.

- Community Engagement, Activation, PR and Communications. The Agency may wish to instruct a specific workstream or task relating to this element for its own landholdings, or it may continue to fall within the scope of joint Consortium appointments. This will be subject to the scope and fees being agreed at the time of confirmation of appointment, subject to value for money assessments at the time.  For Pricing purposes, please assume £30,000 but this will be revisited as the project progresses.

- Staged review process to capture lessons learnt to share internally within the Agency – summary note to be provided. Assume 2 Consultant days.

# Indicative Programme

  - Suppliers should note the indicative programme dates when preparing their Programme information in the Response Form. Suppliers are asked to identify any key risks to delivery of this programme in their response.

| Milestone | Anticipated to be completed by |
| --- | --- |
| Due Diligence review of all information relating to Consortium development of Masterplan | October 2021 |
| Pre-Collaboration Agreement completed | December 2021 |
| Outline Planning Submitted | December 2021 |
| Outline Planning Resolution to Approve* | Summer/ Autumn 2022 |
| Full planning application submitted for the Strategic Infrastructure Works | Autumn 2022 |
|  | To be determined once outline programme on the project has been worked up for both Homes England and the Consortium and as part of the Disposal Strategy to be developed by the Homes England Project team. |
| Outline Planning/ Strategic Infrastructure Works Decision Notices Issued |  |
| Site works commence (infrastructure) |  |
| Approval to Dispose (HE parcel) |  |
| Conditional Contract |  |
| Reserved Matters Submitted |  |
| Reserved Matters Approved |  |
| Start on site |  |
| Final Unconditional Disposal Date |  |

*may be subject to change depending on OPA determination process

# Management

# Homes England Personnel

    - The Supplier will be managed on a day-to-day basis by a named Senior Development Manager who will be identified as the primary point of contact at Homes England. The wider project team includes (please note names will be confirmed after contract award):

- Project Director – project oversight.

- Head of Planning & Enabling – responsible for overall project delivery for this commission for Stage 1&2a

- Head of Disposals – responsible for overall project delivery for this commission for Stage 2b onwards

- Senior Planning & Enabling Manager – Project Manager for Stage 1 & 2

- Senior Development Manager – Providing additional project resource, taking role as Project Manager from Stage 3 onwards

To manage the work flow of information for the various consultant appointments, it will be necessary to set up monthly work stream meetings with the principal leads , to ensure comprehensive collaboration . Please refer to the organogram of the Project Structure at Appendix F

# Other Personnel

    - The Supplier needs to work with the wider Consortium Consultant team.

    - Other key Partners that the Supplier will need to work with include Birmingham City Council, statutory consultees and Consortium Members.

# Meeting Requirements

    - Please note, attendance at the following meetings should be priced within your fee for each Stage of work of The Services as set out at Section 2 above.

Start-up meeting

    - We require two start up meetings, one to be held with Homes England only, and a second ‘consultant’ start up meeting to introduce the wider consultant team and agree project management / governance requirements.  You are required to confirm attendance at these meetings as part of your response.  Please assume each meeting will last for 2.5 hours and will require attendance from your project lead and project manager as a minimum.

Review meetings

    - The requirement for these meetings will change throughout the course of the project and intensify at key milestones.  You are required to confirm attendance at these meetings as part of your response.  For the purpose of evaluation, please assume a fortnightly meeting is required for the duration of the 3-year contract.   Please assume each meeting will last for 2.5 hours and will require attendance from your project lead and project manager as a minimum.

Contract review meeting

    - For the purpose of evaluation, please assume a requirement for quarterly contract review meetings. You are required to confirm attendance at these meetings as part of your response.  Please assume each meeting will last for 2.5 hours and will require attendance from your project lead and project manager as a minimum.

Poor Performance Meeting

    - These meetings will hopefully not be required.  However, if poor performance is repeated following escalation to the Supplier’s Key Personnel to resolve the issue, as required in the Framework Management Schedule of the Framework Contract, the Framework Manager must be notified and Homes England may call for a Poor Performance Meeting.  Beforehand, Homes England will present areas of concern so that the Supplier and Homes England can discuss what happened and why, what will be done to prevent it happening again and how matters will improve.  The Supplier subject to such a meeting would be expected to outline in writing in a Rectification Plan afterwards what improvements/modifications they will be putting in place.  There will be a maximum of two Poor Performance Meetings before termination of the commission.

Break Clause

5.3 .6   There will be break clause applied at the second anniversary of the date of the appointment of this Commission.

# Invoicing

    - This will be agreed at project inception and will include a mix of regular time-based invoicing and fixed fees for key delivery outputs. The successful consultant will keep Homes England informed of spend against budget using the submitted fee schedule format to maintain a clear audit trail.  In the event of key changes in consultant personnel, the consultant will submit an up-to-date fee schedule and attend a meeting to discuss prior to departure of that individual.

5.5   Document Management

5.5.1        As part of the commission there will be a virtual platform for holding all pertinent and relevant data for all of the appointed Consultants (DATA ROOM ) . Homes England platform is called HUDDLE. This platform will grant Admin rights to consultants. Where consultants will be able to upload plans and documents in various forms. This will be further discussed at the start up meeting with the appointed MD Consultant.

# Other Requirements

# Termination

    - Should performance during the period of this appointment prove unsatisfactory following the Poor Performance meeting provisions set out in the Management section above, Homes England will exercise its right under the Termination and Suspension of the Contract clause in the Framework Contract to give notice to terminate the arrangement with immediate effect.

    - If the services are no longer required, for whatever reason, then Homes England reserves the right to terminate the appointment and pay for services completed at that point.

# Conflict of Interest

    - Homes England will exclude the Supplier if there is a conflict of interest which cannot be effectively remedied. The concept of a conflict of interest includes any situation where relevant staff members have, directly or indirectly, a financial, economic or other personal interest which might be perceived to compromise their impartiality and independence in the context of the procurement procedure.

    - Where there is any indication that a conflict of interest exists or may arise then it is the responsibility of the Supplier to inform Homes England, detailing the conflict in a separate appendix  labelled CONFLICT OF INTEREST and signed for return with all other documents through the Pro Contract portal .

# Confidentiality

    - This Further Competition ITT and associated information is confidential and shall not be disclosed to any third party without the prior written consent of Homes England.  Copyright in this Further Competition ITT is vested in Homes England and may not be reproduced, copied or stored on any medium without Homes England's prior written consent.

    - Suppliers shall not undertake, cause or permit to be undertaken at any time any publicity in respect of this Further Competition process in any media without the prior written consent of Homes England.

# Variations to Scope of Services

    - Note that it is recognised that as the commission progresses and the disposal strategy evolves, the scope of works may change and as such Homes England retain the ability to discuss any amendments beyond what has been priced for in this tender with the appointed consultant at the appropriate time. Provision has therefore been made to amend / extend the scope of the commission either through supplementing existing or adding new work stages.

    - Bidding Suppliers are NOT asked to price for any changes at this stage.  If these services are required this will be discussed with the appointed consultant.

    - Although any changes are anticipated to remain with this existing scope (i.e. one phase delayed), if any additional work is required, it will be subject to further agreement/approval by the Agency in writing and via TMS and will be based on value for money assessments. Additional work will be commissioned at hourly/daily rates directly related to the scope of works required and agreed.

    - Please note, additional scope of works will be up to a maximum of 50% of the original instruction, in order to remain compliant with Agency Procurement requirements.

# Part 2 - Instructions for Submitting a Response

# General

  - The Further Competition deadline is 12 NOON on 13th July 2022 and tender responses must be submitted on ProContract.  Please regularly check ProContract for any amendments to the Further Competition deadline. For all ProContract portal issues please contact ProContractSuppliers@proactis.com.

  - Suppliers must ensure that suitable provision is made to ensure that the submission is made on time.  Any tender responses received after the Further Competition deadline shall not be opened or considered unless Homes England, exercising its absolute discretion, considers it reasonable to do so.  Homes England, may, however, at its own absolute discretion extend the Further Competition deadline and shall notify all Suppliers of any change via ProContract.

  - Please note all communications during the tender period will be via the ProContract website. All Suppliers that have registered their interest for the Procurement will receive a direct email notification from ProContract on any updates via the Suppliers registered email address.  No approach of any kind should be made to any other person within, or associated with, Homes England.  It is the Suppliers responsibility to check the ProContract website for any updates to the Procurement process.  No claim on the grounds of lack of knowledge of the above-mentioned item will be entertained.

  - The Consultant  should check the Further Competition ITT for obvious errors and missing information.  Should any such errors or omissions be discovered the Supplier must send a message via the messaging function on ProContract.  No alteration may be made to any of the documents attached thereto without the written authorisation of Homes England.  If any alterations are made, or if these instructions are not fully complied with, the tender response may be rejected.

  - Tender responses must not be accompanied by statements that could be construed as rendering the tender response equivocal and/or placing it on a different footing from other Suppliers.  Only tender responses submitted without qualification strictly in accordance with the Further Competition ITT (or subsequently amended by Homes England) will be accepted for consideration.  Homes England’s decision on whether or not a tender response is acceptable will be final.

  - Tender responses must be written in English.

  - Under no circumstances shall Homes England incur any liability in respect of this Further Competition or any supporting documentation.  Homes England will not reimburse the costs incurred by Suppliers in connection with the preparation and submission of their tender response to this Further Competition.

  - Homes England reserves the right to cancel this Further Competition process at any time.

Clarifications

1.9	All clarification requests must be sent using ProContract no later than 5 working days before the Further Competition deadline shown on ProContract.  Any queries submitted after this may not be answered.  Homes England will respond to clarifications as soon as practicable.

1.10	Suppliers should specify in their clarification questions if they wish the clarification to be considered as confidential between themselves and Homes England. Homes England will consider any such request and will either respond on a confidential basis or give the Supplier the right to withdraw the clarification question.  If the Supplier does not elect to withdraw the question and Homes England considers any clarification question to be of material significance, both the question and the answer will be communicated, in a suitably anonymous form, to all prospective Suppliers who have responded.  If Suppliers consider that page limits set out in Section 20 (Evaluation Criteria) are insufficient to provide the information required by the question, then a clarification request should be raised.  No guarantee can be given that the page limit will be increased.

# Quality

  - A Response Form template Appendix G has been provided in Part 2 to respond to the Quality questions detailed in Section 20 (Evaluation Criteria).  The Response Form must be completed and returned as part of the tender response.

  - Suppliers must provide information on proposed staff in the Response Form and Resource and Pricing Schedule provided in Part 2.  Appendix H If the Consultant  is a Consortium or intends to sub-contract the Services, in whole or in part, then it should specify precisely in the Resource and Pricing Schedule which economic operator shall perform the Services (or parts thereof).

  - PLEASE NOTE: The Resource and Pricing Schedule will be scored qualitatively as part of the overall quality response. The schedule lists out the services that are required for the financial bid, the appropriateness of the quantum and seniority of resource will be scored as part of the quality bid.  For example, if a particular workstream does not have an appropriate time resource or seniority allocated, it can be scored down.

# Pricing

  - A Resource and Pricing schedule has been provided with this Further Competition ITT which must be completed and returned as part of the tender response.  Please note comments above that state that  the allocation of resource will be part of the quality evaluation.

  - The pricing approach for this Further Competition is a lump sum fixed fee for each stage of work, supported by a resourcing schedule to evidence time allocation for each proposed team member.   An allowance should be included for expenses as part of the overall fee proposal, please note these will not be chargeable separately unless agreed in advance by Homes England and in exceptional circumstances where there is demonstrable need for the increased expense. It is anticipated that fees will be paid monthly in arrears, up to the satisfactory completion of specific milestones/ tasks/ packages of work.

  - The list of activities in the Resource and Pricing Schedule is not exhaustive and there may be additional duties/services required that will emerge as work is undertaken.  This commission may be extended on client instruction to cover such matters as arise, based on a time charged fee schedule completed in the tender response.  The commission will only be extended if the services relate to the original objective of the overall call off contract.

  - Suppliers are reminded that day rates for all individuals must be the agreed Framework Contract rates unless discounted rates are offered and will be used for all of the services.

# Evaluation

  - Tender responses will be evaluated on the basis of the overall most economically advantageous Tender (MEAT) submitted to Homes England.  The evaluation criteria (and relative weightings) that Homes England will use to determine the most economically advantageous Tender are set out in Section 5  (Evaluation Criteria) below and the scoring approach is detailed in Worked Example).  Scores will be rounded to two decimal places.

  - Evaluators will initially work independently. Once they have completed their independent evaluation they will meet to discuss, understand and moderate any differences they have via a consensus meeting, where a single consensus score for each question will be agreed.

  - Award decisions will be subject to the standstill period if over the Services threshold.  Unsuccessful Framework Suppliers will be provided with their scores and feedback to explain the award decision.

  - Homes England is mindful that one Consultancy may not have access to all of the expertise needed to fulfil this brief. Homes England encourages Suppliersto collaborate as needed to ensure the highest level of advice in each of the areas highlighted as defined within the scope of services. The MD Lead Consultant will oversee the appointed Personnel as well as utilise specialist Sub-Suppliersas required throughout the project. The appointment of any sub-Supplierswill need to be approved by Homes England, and this review forms part of the evaluation process.

  - Interviews may be carried out as part of the process, and these will be undertaken after the submission of the return, as shown in the timetable below. The interview will be an opportunity for each of the Consultant firms to present their proposals to support the return submitted.  A question sheet will be provided to all tenderers 4 working days prior to the session.

Procurement Timetable

The procurement timetable that Homes England is working towards is set out below; this timetable is subject to change.

| Stage | Milestone | Anticipated Dates |
| --- | --- | --- |
| Stage 2 – Sifting | Issue Sifting Brief | 9th March 2022 |
|  | Return Deadline | 25th March 2022 |
|  | Notification of successful bidders | 13th April 2022 |
| Stage 3 - ITT | Issue Invitation to Tender | 1st June 2022 |
|  | Clarification Period | Ends on Friday 6h July 2022 |
|  | Submission Deadline | 13th July 2022 |
|  | Interviews (at Homes England Coventry Office) | 28th/ 29th July 2022 |
|  | Notification of successful bidder | 12th August 2022 |
|  | End of Standstill* | 10 days post notification (26th August 2022) |
|  | Start-up meetings | w/c 5th September 2022 |

* The appointment will require both Project Director (internal) and Cabinet approval. This will be obtained during the 10-day Standstill period.

  - ProContract will provide the most up to date information regarding timescales.

# Evaluation

  - Suppliers are expected to provide the following information in response to this Further Competition ITT:

- Completed Response Form   Appendix G

- Completed Resource and Pricing Schedule Appendix H

# 5. 2 Evaluation Criteria

| Quality will account for 70 % of the Overall Score. The following scoring methodology will apply: 5 – Excellent Satisfies the requirement and demonstrates exceptional understanding and evidence in their ability/proposed methodology to deliver a solution for the required supplies/services. Response identifies factors that will offer potential added value, with evidence to support the response. 4 – Good Satisfies the requirement with minor additional benefits. Above average demonstration by the Consultant of the understanding and evidence in their ability/proposed methodology to deliver a solution for the required supplies/services. Response identifies factors that will offer potential added value, with evidence to support the response. 3 – Acceptable Satisfies the requirement. Demonstration by the Consultant of the understanding and evidence in their ability/proposed methodology to deliver a solution for the required supplies/services. 2 - Minor Reservations Some minor reservations of the Supplier’s understanding and proposed methodology, with limited evidence to support the response. 1 – Major Reservations/Non-compliant Major reservations of the Supplier’s understanding and proposed methodology, with little or no evidence to support the response. 0 - Unacceptable/Non-compliant Does not meet the requirement. Does not comply and/or insufficient information provided to demonstrate that the Consultant has the understanding or suitable methodology, with little or no evidence to support the response. PLEASE NOTE IF YOUR RESPONSE SCORES 1 or 0 FOR ANY ONE QUESTION YOUR OVERALL SUBMISSION WILL BE DEEMED AS A FAIL. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Number | Criteria | Demonstrated by | Weighting |
| 1 | Technical Understanding To provide a Method Statement in how you will deliver the proposed services, providing details, highlighting interdependencies and critical path. Include key project risks and issues as part of your response. The proposal should be a maximum of 6 sides of A4 with Arial font size 11 single spacing Appendices accepted – Maximum of 5 sides same format as above | Homes England consider the following as key areas of activity requiring technical services support, and to support the QA desk top review. Please refer to the Homes England schedule of tasks in each of the elements to ensure that all known tasks are covered; this list is not exhaustive. Categories are - Technical and Site Investigation to include the Infrastructure Works - Ecology - Project Coordination and Cost Management - Development/ Compliance Monitoring - Disposals - Master Planning and Urban Design - CDM and Health and Safety Please highlight any additional tasks considered to be significant and pivotal to the delivery of the Commission, and their relevance to the success of the delivery of the project, including any cost and risk impact. That demonstrates the importance of need to be fully considered as part of the task / activities identified. And please insert into the resourcing schedule as indicated within Appendix H | 30% |
| 2 | Resource and Resource Coordination Maximum page limit = 6 sides of A4 size 11 Arial font single spacing including any tables and diagrams (excluding CVs) | Within this answer, you will need to detail how the Commission would be coordinated and managed. In your response you will need to offer succinct details of how the whole commission will be managed by your Lead Consultant together with realistic contingency arrangements. - Who will lead the overall Commission from the MD Consultant, and report back to the Homes England Team on a monthly basis as shown in the Homes England organgram at Appendix F on all elements of the commission - Set out the reporting/ coordination arrangements, for the proposed MD team to any subconsultants. - Where subconsultant arrangements are proposed, please set out how this will be managed by the Principal MD Consultant to ensure that HE requirements are met. The evaluation process shall closely look at your proposed internal resource and assess the risks and benefits you face with any of your sub-consultants. A proposed organogram with reporting lines shall enhance the evaluation process together with the resource planning management you intend to adopt to ensure anticipated future progress remains ‘on-track’. Include any matters you anticipate facing throughout this project including realistic periods for recruitment. Please note that any personnel mentioned in the structure provided must correspond with the Pricing and resourcing schedule. Capacity Management – Please describe how you propose to manage the ebb and flow of the information provided/ required outputs to ensure that resource capacity is managed and maintained over the duration of the appointment. Performance- Please describe how you will seek to maintain good performance on all tasks and activities that are to be carried out, whether they be by employees or subSuppliersfor the duration of the project. | 30% |
| 3 | Programme/Timescales Provide a comprehensive programme which demonstrates your understanding of the project and key milestones which need to be achieved (Project Programme with critical path must be included). Maximum page limit = 4 sides of A4 size 11 Arial font single spacing | A provisional delivery programme is currently being discussed with the Consortium, which expands on Section 3. The following detailed information is sought in your response to this question: - How will you ensure the team gets up to speed following appointment, given the need to review a large volume of technical information which will accompany the full strategic infrastructure application (to be submitted in the autumn)? - Please set out appropriate critical path points to ensure the required planning approvals are secured and development is physically delivered on site thereafter. Set out key risks to achieving this programme and how you will proactively mitigate these. | 10% |

| Price will account for 30% of the Overall Score. The lowest price will gain the maximum marks with other prices expressed as a proportion of the best score using the maths explained in the worked example below. |  |  |
| --- | --- | --- |
| Criteria | Demonstrated by | Weighting |
| Price | Completed Resource and Pricing Schedule detailing each of the elements of the scope separately Please submit this in as a PDF and Excel format. Please ensure that the personnel corresponds with the responses to questions 2 and 3 , to include seniority and specialist expertise and advise where necessary where a sub consultant | 30% |

Worked Example

How your quality scoring will be used to give a weighted score

| Bidder | Question | Score out of 5 | Weighting | Weighting Multiplier | Weighted Score | Total Weighted Score |
| --- | --- | --- | --- | --- | --- | --- |
| Supplier A | 1 | 2 | 30% | 6 | 12 | 27 |
|  | 2 | 3 | 30% | 2 | 6 |  |
|  | 3 | 3 | 10% | 3 | 9 |  |
| Supplier B | 1 | 5 | 30% | 6 | 30 | 5 0 |
|  | 2 | 4 | 30% | 2 | 8 |  |
|  | 3 | 4 | 10% | 3 | 12 |  |
| Supplier C | 1 | 2 | 30% | 6 | 12 | n/a (fail)* |
|  | 2 | 1 | 30% | 2 | n/a |  |
|  | 3 | 2 | 10% | 3 | 6 |  |

* in the example above Supplier C’s pricing will not be scored

Worked example of how your price will be used to calculate a score

| Bidder | Form of Tender price | Lowest price/Supplier’s price (as %) | Price Score (out of 30) |
| --- | --- | --- | --- |
| Supplier A | 350 | 350/350 = 100% | 100%*30 = 30 |
| Supplier B | 700 | 350/700 = 50% | 50%*30 = 15 |
| Supplier C | 250 | n/a | n/a |

Worked example of Overall Score and Ranking

| Bidder | Total Quality Score | Price Score | Total Score | Ranked Position |
| --- | --- | --- | --- | --- |
| Supplier A | 27 | 30 | 57 | 2 |
| Supplier B | 50 | 15 | 65 | 1 |
| Supplier C | n/a | n/a | n/a | n/a |

# Part 3 Response Form

# Appendix G - RESPONSE FORM

To enable Homes England to evaluate your tender, we require Suppliers to respond to the questions below whilst making reference to the evaluation section above. Homes England will accept responses in your own format, but you will have to comply with the page limit and font size outlined in the evaluation section.

| Framework | 2018- 23 Multidisciplinary Services Framework 2018/S127-289621 |
| --- | --- |
| Project Title | Langley SUE, Planning, Design and Technical Support / Quality Assurance |
| Pro Contract Number | DN 596695 |
| Supplier | Supplier insert |
| Date | Supplier insert |

Question 1 Technical Understanding

Question 2 Resource and Resource Coordination

Question 3 Programme / Timescales

Appendix A   Infrastructure Works Plan

Appendix B - Constraints Plans

Appendix C - Scope of Services Detail Information

Appendix D- Principal Designer Role

Appendix E - Disposal Technical Pack

Appendix F – Project Structure Organogram

Appendix G - Response Form

Appendix H – Resource and Pricing Schedule

enquiries@homesengland.gov.uk

0300 1234 500

gov.uk/homes-england