**Specialist PPE Revised Indicative Timetable**

|  |  |  |
| --- | --- | --- |
| **Activity** | **Indicative Start Date** | **Indicative End Date** |
| **Publish OJEU–** **Restricted Procedure  - Groups 1-4** | 21st  February 2020 |
| **Request for SQ responses**  | 24th February 2020 | 12 noon – 24th  March 2020 |
| **Deadline for tenderer’s clarification questions (SQ)** | 17.00hrs 10th March 2020 |
| **Evaluation of SQ, Short-List Bidders and Notify Bidders of Outcome**  | 25th March 2020 | 17th April 2020 |
| **Invitation To Tender - Timescales for Tender responses** | 20th  April 2020 | 12 noon – 20th  May 2020 |
| **Sizing** | 20 April 2020 | 24th April 2020 |
| **Deadline for tenderer’s clarification questions (ITT)** | 17.00hrs 6th May 2020 |
| **Initial ITT Evaluation of Mandatory requirements** | 21st  May 2020 | 12th June 2020 |
| **Notification of outcome of evaluation of ITT mandatory requirements** | w/c 22 June 2020 |
| **Production of samples for testing & trialling (from end of sizing event to delivery, 12 weeks)**  | 24th April 2020 | 17th  July 2020 |
| **Submission of Test Certificates to the Authority** | 12 noon 17th July 2020 |
| **Fitting Event**  | 20th July  2020 | 24th July 2020 |
| **Testing & Trialling of Lots** | 27th July 2020 | 14th August 2020 |
| **Evaluation and Moderation of Lots** | 17th August 2020 | 28th August 2020 |
| **Notification of Preferred Supplier Status**  **Commencement of Alcatel**  | 1st September 2020 |
| **End of Alcatel and Notification of Framework Award**  | 11th September 2020 |
| **Issue of Contracts** | w/c 14th September 2020 |