| Refurbishment of 49-59 Old Street SCHEDULE OF WORKS |
| --- |
|  | Purpose of this Document |  |
|  | Use this document as an aid to summarise the scope of works. Complete the Cost Sum Analysis (Appendix L) and the Electrical and Mechanical Tender Summaries (Appendix D) to summarise costs. |  |
| 1.0 | Preliminaries |  |
| 1.1 | Costs associated with project preliminaries (Section 2) contained in Appendix O: |  |
|  | A40: |  |
|  | A41: |  |
|  | A42: |  |
|  | A43: |  |
|  | A44: |  |
| 1.2 | Drawings and Pricing: Price All items on all Drawings In addition to the broad areas of work headlined in the scope of works below ensure all items indicated on the following architectural, electrical, mechanical and structural drawings in conjunction with the associated specifications are priced: ITT 4 Appendix B – Existing and Proposed Architectural Plans ITT 4_Appendix 8_14507_JW_1 - Existing Basement Plan ITT 4_Appendix B_14507_JW_2 - Existing Ground Floor Plan ITT 4_Appendix B_14507_JW_3 - Existing First Floor Plan ITT 4_Appendix 8_14507_JW_4 - Existing Second Floor Plan ITT 4_Appendix 8_14507_JW_5 - Existing Third Floor Plan ITT 4_Appendix B_14507_JW_6 - Existing Fourth Floor Plan ITT 4_Appendix B_14507_JW_7 - Existing Fifth Floor Plan ITT 4_Appendix 8_14507_JW_8 - Existing Sixth1 Floor Plan ITT 4_Appendix B_14507_JW_9 - Existing Roof Plan ITT 4_Appendix 8_14507_JW_10 - Existing Elevations ITT 4_Appendix 8_14507_JW_11 - Existing Sections ITT 4_Appendix B_A1.1 Site Location Plan ITT 4_Appendix B_A1.2 Location of Swing Gate and Cycle Enclosure ITT 4_Appendix B_A1.09 Basement Demolition Plan ITT 4_Appendix B_A1.10 Ground Floor Demolition Plan ITT 4_Appendix B_A1.11 First Floor Demolition Plan ITT 4_Appendix B_A1.12 Second Floor Demolition Plan ITT 4_Appendix B_A1.13 Third Floor Demolition Plan ITT 4_Appendix B_A1.14 Fourth Floor Demolition Plan ITT 4_Appendix B_A1.15 Fifth Floor Demolition Plan ITT 4_Appendix B_A1.16 Sixth Floor Demolition Plan ITT 4_Appendix B_A1.17 Roof Demolition Plan ITT 4_Appendix B_A1.099 Proposed Plan Basement ITT 4_Appendix B_A1.100 Proposed Plan Ground Floor ITT 4_Appendix B_A1.101 Proposed Plan First Floor ITT 4_Appendix B_A1.102 Proposed Plan Second Floor ITT 4_Appendix B_A1.103 Proposed Plan Third Floor ITT 4_Appendix B_A1.104 Proposed Plan Fourth Floor ITT 4_Appendix B_A1.105 Proposed Plan Fifth Floor ITT 4_Appendix B_A1.106 Proposed Sixth Floor Plan ITT 4_Appendix B_A1.107 Proposed Roof Plan ITT 4_Appendix B_A1.200 Fire Strategy Ground Floor Plan ITT 4_Appendix B_A1.201 Fire Strategy Upper Floor Plans 1, 2, 3, 4, 5, 6 ITT 4_Appendix B_A2.10 Demolition North East Elevation ITT 4_Appendix B_A2.11 Demolition South West Elevation ITT 4_Appendix B_A2.12 Demolition South East Elevation ITT 4_Appendix B_A2.13 Demolition North West Elevation ITT 4_Appendix B_A2.100 Proposed North East Elevation ITT 4_Appendix B_A2.101 Proposed South West Elevation ITT 4_Appendix B_A2.102 Proposed South East Elevation ITT 4_Appendix B_A2.103 Proposed North West Elevation ITT 4_Appendix B_A4.100 Staircase Plans & Sections E-E' & F-F’ ITT 4_Appendix B_A4.101 First Floor Balustrade & Roof Deck Layout Sheet 1 ITT 4_Appendix B_A4.102 First Floor Balustrade & Roof Deck Layout Sheet 2 ITT 4_Appendix B_A4.103 Seventh Floor Roof and Balustrade Layout ITT 4_Appendix B_A4.104 First Floor Balustrade Elevations ITT 4_Appendix B_A4.105 Seventh Floor Balustrade Elevations ITT 4_Appendix B_A4.200 Washrooms Plans & Elevations ITT 4_Appendix B_A4.201 Disabled WC & Shower Plans & Elevations ITT 4_Appendix B_A4.300 Kitchenette Plans & Elevations ITT 4_Appendix B_A5.100 Balustrade Steelwork ITT 4_Appendix B_A5.101 Balustrade & Waterproofing Details ITT 4_Appendix B_A5.200 Glass Enclosure Details ITT 4_Appendix B_A6.100 Door Elevations and Jamb Details ITT 4_Appendix B_A6.101 Door & Ironmongery Schedule ITT 4_Appendix B_A6.200 Window Elevations Sheet 1 ITT 4_Appendix B_A6.201 Window Elevations Sheet 2 ITT 4_Appendix B_A6.202 Window Details ITT 4_Appendix B_A7.100 Dry Lining Details ITT 4_Appendix B_LBI Architectural Drawing Document Issue Receipt Record ITT 5 Appendix C – National Building Specification ITT 6 Appendix D – Mechanical and Electrical Drawings and Specification Mechanical Documents ITT 6 Appendix D Section M2 – Particular Specification for Mechanical Engineering and Plumbing Services at 49-59 Old Street, Islington ITT 6 Appendix D 17312/100 Boosted cold water schematic ITT 6 Appendix D 17312/101 Above ground drainage schematic ITT 6 Appendix D 17312/102 Unvented water heaters safety discharge drainage schematic ITT 6 Appendix D 17312/103 Above ground drainage ground floor level ITT 6 Appendix D 17312/104 Above ground drainage first floor level ITT 6 Appendix D 17312/105 Above ground drainage second floor level ITT 6 Appendix D 17312/106 Above ground drainage third floor level ITT 6 Appendix D 17312/107 Above ground drainage fourth floor level ITT 6 Appendix D 17312/108 Above ground drainage fifth floor level ITT 6 Appendix D 17312/109 Above ground drainage sixth floor level ITT 6 Appendix D 17312/110 Hot & cold water services ground floor level ITT 6 Appendix D 17312/111 Hot & cold water services first floor level ITT 6 Appendix D 17312/112 Hot & cold water services second floor level ITT 6 Appendix D 17312/113 Hot & cold water services third floor level ITT 6 Appendix D 17312/114 Hot & cold water services fourth floor level ITT 6 Appendix D 17312/115 Hot & cold water services fifth floor level ITT 6 Appendix D 17312/116 Hot & cold water services sixth floor level ITT 6 Appendix D 17312/117 Typical floor layout ac and heating. ITT 6 Appendix D 17312/118 AC and heating roof level units ITT 6 Appendix D 119 Basement hot and cold water layout Electrical Documents ITT 6_Appendix D 17020/202 A1 Basement - Power/Data layout ITT 6_Appendix D 17020/203 A1 Ground Floor Power/Data layout ITT 6_Appendix D 17020/204 A1 First Floor Power/Data layout ITT 6_Appendix D 17020/205 A1 Second Floor Power/Data layout ITT 6_Appendix D 17020/206 A1 Third Floor Power/Data layout ITT 6_Appendix D 17020/207 A1 Forth Floor Power/Data layout ITT 6_Appendix D 17020/208 A1 Fifth Floor Power/Data layout ITT 6_Appendix D 17020/209 A1 Sixth Floor Power/Data layout ITT 6_Appendix D 17020/210 A1 Roof Power/Data layout ITT 6_Appendix D 17020/211 A1 Basement - Lighting layout ITT 6_Appendix D 17020/212 A1 Ground Floor Lighting layout ITT 6_Appendix D 17020/213 A1 First Floor Lighting layout ITT 6_Appendix D 17020/214 A1 Second Floor Lighting layout ITT 6_Appendix D 17020/215 A1 Third Floor Lighting layout ITT 6_Appendix D 17020/216 A1 Forth Floor Lighting layout ITT 6_Appendix D 17020/217 A1 Fifth Floor Lighting layout ITT 6_Appendix D 17020/218 A1 Sixth Floor Lighting layout ITT 6_Appendix D 17020/219 A1 Roof Lighting layout ITT 6_Appendix D 17020/220 A1 Mains Distribution Schematic ITT 6_Appendix D - Electrical Trade Preambles E1 ITT 6_Appendix D - Electrical Detailed Specification E2 ITT 6_Appendix D - 17020/221 A1 Trenching Detail ITT 7 Appendix E – Structural Drawings and Specification ITT 7 Appendix E APPENDIX A Photographs ITT 7 Appendix E APPENDIX B Drawings ITT 7 Appendix E APPENDIX C Product Information ITT 7 Appendix E APPENDIX D NBS Specification ITT 7 Appendix E APPENDIX E Structural Repair Specification ITT 7_Appendix E_Architects dwg. A5.101 Balustrade Waterproofing Details.pdf- E+M requirements |  |
| 2.0 | Clearance / Demolition |  |
| 2.1 | Temporary Protection Construct temporary containment suitable to carry out demolitions as shown on demolition drawings. |  |
| 2.2 | Existing Partitions Remove all existing partition walls to including all fixtures and fittings, floor coverings (including all previously laid coverings and all old board material onto which coverings were laid), entrance matting, sanitary ware etc. and cart away (for all demolition items see demolition drawings A1.09, A1.10, A1.11, A1.12, A1.13, A1.14, A1.15, A1.16, A1.17. and specification section C20). Make good to plasterwork and finishes to all remaining columns and partition walls when demolition has been under-taken, as per specification section M20. Make good to plaster partitions where partitions have been demolished. |  |
| 2.3 | Sanitary Ware |  |
|  | Demolish and cart away all sanitary fittings and general fittings. |  |
| 2.4 | Wall Tiling |  |
|  | Remove and cart away all existing ceramic wall tiles to WC’s and kitchen areas. Make good plaster to receive new tiling. |  |
| 2.5 | Internal Door sets & External Doors |  |
|  | Carefully remove and cart away existing door-sets (both internal and external entrance door sets (front and rear) and to roof where indicated on drawings. |  |
| 2.6 | Floor Coverings including floor tiling. |  |
|  | Remove all existing floor coverings including matting and fixed terracotta floor tiling to the ground floor and all WC/ bathroom areas to all floors. |  |
| 2.7 | Loose Furniture, fittings and all other loose items. |  |
|  | Remove and cart away all loose furniture, fittings and all other loose items etc. |  |
| 2.8 | Existing Steel Crittall Windows and Crittall Doors |  |
|  | Remove and cart away all existing Crittall windows and Crittall doors including those to the rear, basement level elevation of café unit. |  |
| 2.9 | Existing WC overflow Pipes |  |
|  | Remove all existing WC overflow pipes and make good with mortar matched to brick. |  |
| 2.10 | All Existing Mechanical, Electrical, Digital, Security and Fire services. |  |
|  | Remove all existing services including all trunking, fittings, pipework etc. (See M&E / ICOM / Chubb Security / T&P Fire specifications to ensure no double counting) |  |
| 2.11 | Existing Bike Stands |  |
|  | Remove existing bike stand to rear of block. |  |
| 2.12 | Existing Dry Riser cupboard doors |  |
|  | Remove existing dry riser cupboard doors to each landing. |  |
| 2.13 | Cut back Roof slab & associated demolition – Tank Room at 7th floor Roof Level |  |
|  | Cut back roof slab at roof level. Remove and cart away. Note: existing Roof slab: Reinforced concrete slab 130-150mm thick, incl. 10mm plastered ceiling with steel filler joists @ 400mm centres. Remove and cart away redundant roof water tanks. Remove and cart away brick support dwarf walls. |  |
| 3.0 | NEW WORKS |  |
|  | EXTERNAL ENVELOPE |  |
| 3.1 | New Aluminium Windows and Doors |  |
|  | Supply and fix new double glazed aluminium frame windows throughout, including doors to roof areas at first floor level, as per Proposed Elevations drawings A2.100, A2.101, A2.102 and A2.103 and L10/330A. |  |
| 3.2 | Brickwork & Concrete Cills |  |
| 3.2.1 | Allow 300m of pointing to match existing pointing. Pointing to brickwork – provide Cost /m |  |
| 3.2.2 | Allow 300m of pointing to match existing pointing. Pointing to concrete cills – provide Cost /m |  |
| 3.2.3 | Repair 600mm x 700mm brick opening at First Floor level, to North-West Elevation with bricks to match existing. |  |
| 3.3 | Top floor Roof & first floor roofs |  |
|  | Carry out all works as described in Appendix K – IKO Roof Report//Polimar EC/UV Remedial Specification. Proposal Summary: • Main (High Level) Roof Area – Prepare and overlay existing bitumen membrane waterproofing, with IKO Polimar EC/UV liquid waterproof coating (no insulation upgrade) • Low Level Roofs 1 and 2 – Remove existing bitumen membrane overlay back to the underlying asphalt, and prepare and overlay original asphalt, with IKO Polimar EC/UV liquid waterproof coating (no insulation upgrade) • Tank House/Lift Motor Room Roof Areas – Prepare and overlay existing bitumen membrane waterproofing, with IKO Polimar EC/UV liquid waterproof coating (no insulation upgrade) • New liquid waterproof coating to be applied to all flat roof areas and detail work • Increase upstand heights to door threshold (Low Level Roofs only) • Create new emergency overflow chutes through parapet walls adjacent to existing outlets (Low Level Roofs only) The works must comply with the requirements of the Health and Safety at Work Act and specific requirements as set out by the client. All risk assessments must be undertaken and recorded by the installing contractor. MAIN CONTRACTOR WORKS Brick Abutments – Cut new chase in brickwork abutments, to receive new IKOflash lead free flashings (by roofing sub-contractor). Cables - Temporarily remove or divert sundry cables/satellite dishes and set aside for re-use or disposal as directed by client. Freestanding Staircase (Main Roof) – Decommission and temporarily remove roof surface mounted staircase and set aside for adjustment and reinstatement on completion of the works. Existing Deck Fixed Handrail (Main Roof) – When the project scaffolding is in place, remove the existing deck fixed handrails and in conjunction with the roofing sub-contractor, make good openings in the waterproofing system. Existing Freestanding Handrail (Main Roof) – When the project scaffolding is in place, remove existing freestanding handrail and set aside for re-use or disposal as directed by client. Installation of New Deck Fixed Handrails (Main Roof) – At designated locations, cut through the existing waterproofing and screed to expose the structural slab level to allow the installation of the new handrail posts. NB. This work must be carried out in conjunction with the roofing sub-contractor to make good openings in the waterproofing system and installing insulation to the same thickness as surrounding areas. NOTE: This opening-up/enabling work must also be done in a timely fashion to allow CA to assess depth of screed to finalise design of steelwork and decking levels & details. Existing Parapet Wall Fixed Handrails (Low Level Roofs) – Augment existing handrails as required meeting current Building Regulation guidelines for the proposed roof usage. Access Door Thresholds (Low Level Roofs) - Raise the position of existing door thresholds, using treated timber, to give a minimum upstand height of 150mm/75mm above the surface of the completed waterproofing. Install new doors and frames in accordance with the client specification given separately. Emergency Drainage Chutes (Low Level Roofs Only) – Cut new emergency overflow chutes through parapet walls adjacent to existing outlets and install flanged lead sleeves. ROOFING CONTRACTOR WORKS – TO BE PRICED FOR AND OVERSEEN BY MAIN CONTRACTOR Outlets – Clean and open up roof around all outlets to the maximum extent of the internal down pipes and install new IKO Refurbishment Outlets. Preparation Main Roof Prepare the existing BUR waterproofing. Remove all surface moss, dirt and debris. Star cut and seal blisters/ridges in the existing waterproofing to receive the overlay system. Lower Level Roofs Remove existing overlay BUR waterproofing back to the original asphalt on the main flat roof areas. BUR waterproofing to remain in place for overlay on the parapet walls. Prepare the original asphalt. Remove all dirt and debris. Blisters/ripples in the asphalt should be carefully warmed, pierced and smoothed down to a level surface to receive the overlay system. Roofs containing moss or algal growth must be treated with a fungicidal. wash and allowed to dry before applying the Polimar liquid coating. Use Polimar KRM reinforcing mesh or a 250mm wide strip of 225g/m² GRF Reinforcement over cracks or splits in the existing waterproofing, bedded in Polimar EC. A peel test must be carried out to ensure a good bond can be achieved. Surfaces to receive waterproofing must be clean, smooth and dry. Additional Roof Repairs (non-IKO) Main Roof Repairs – Flashing required to entire perimeter of skirting to Elastomeric felt roof upstands around plant room. Replace 5m section of Tank room roof guttering to match existing. Install a lead-flashing and welted drip detail to corner of brick joint to canopy and brickwork. Prime concrete overhang and re-decorate as Appendix M First floor roofs: Concrete repairs required to concrete-beam and cornice detail – as structural engineer’s details. |  |
| 3.3.1 | New Balustrades & Decking to Seventh Floor Roof and First Floor Roofs Install new steelwork and balustrade/decking & decking supports as detailed on dwgs: A4.101 First Floor Roof Deck and Balustrade Layout - Sheet 1 A4.102 First Floor Roof Deck and Balustrade Layout - Sheet 2 A4.103 Seventh Floor Roof Deck and Balustrade Layout A4,104 Elevations of Balustrade First Floor (Handed for LHS) A4.105 Elevations of Balustrade Seventh Floor Provide and fix timber decking on adjustable decking supports and Q-Railing structural glass balustrade as dwgs. A5.100, A5.101 |  |
| 3.4 | Front Entrance Door |  |
|  | Supply and fix new fob-operated automatic fully glazed door Glass Door to Front Entrance L20/491. |  |
| 3.4.1 | Stainless steel panels to either side of Front Entrance Door |  |
|  | Supply and fix full height brush stainless steel panels to either side of glazed front entrance door. Include for all opening for access control panel and letter box. See drawing A6.100 |  |
| 3.5 | Rear Entrance Doors |  |
|  | Supply and fix 4no. steel rear entrance doors to rear elevation. |  |
| 3.6 | Not used |  |
| 3.7 | Decoration to cills and window heads |  |
|  | Decorate all cills and window head surrounds with Dulux Trade Masonry Paint as Appendix M |  |
| 3.8 | Cleaning to brickwork Structural Engineer’s schedule and specification as Appendix E |  |
|  | Clean all external brickwork, soffits, cills, heads etc. generally and to remove pollutants accumulated arising due to splashback and long term water ingress & hard water scale/salt deposit staining. In addition, apply semi-permeable silicon based water repellent system to brickwork 5-courses below each cill. Steam-clean concrete undercroft over access road and walls to rear of building. |  |
| 4.0 | INTERNAL WORKS |  |
|  | Partitions |  |
| 3.1 | Solid Partitions WT1 - 105.5mm & WT2 - 111mm thick |  |
|  | Partition Type WT1 Form new 105.5mm thick full height drywall partitions at 2850mm high. (Includes 18mm WBP plywood to one side only sides of stud). Finish walls ready for decoration as per clause K10 / 127A. Partition Wall details to include all necessary abutments to walls, floor and structural slab, and for forming of door openings. Partition Type WT2 Form new 111mm thick full height drywall partitions at 2850mm high. (Includes 18mm WBP plywood to both sides of stud). Finish walls ready for decoration as per clause K10 / 127B. Partition Wall details to include all necessary abutments to walls, floor and structural slab, and for forming of door openings. |  |
| 3.1.1 | New Skirtings Include for a 100 x 25mm softwood skirting P20/ 111, painted M60/121 to ALL new partitions. |  |
| 3.2 | Kitchenettes |  |
|  | New Kitchenettes to each Business Unit and Roof Top (Old Plant Room). (14no.) Supply and install kitchenettes at all floor levels. Sink / Sink Base Unit / 3no. 600mm base units 5no. 600mm wall units, Corian work surface & splashback. as per dwg. A4_300 and spec N11/ 340. Include for an additional number of units for Roof top room as shown on dwg A1.107 |  |
| 3.3 | WC Facilities |  |
|  | Supply and fix New Sanitary Ware to WCs and associated pipework and partitions etc. as per dwg. A4_200 and specification N13 to all Business Units (12 no.) Supply and fix all associated fittings as shown on A4.200, |  |
| 3.4 | Shower Facilities at Entrance / GF level |  |
|  | Form new partitions and supply and fix New Sanitary Ware to disabled WC n13/311 and associated fittings as shown on A4.201 One shower facility and associated fittings and fixtures as per drawing A4.201 and N13/375 |  |
| 3.5 | Internal Doors |  |
| 3.5.1 | Interior timber Fire Door Set Door Sets Supply and install interior timber door sets finished ready to receive paint finish solid core doors as per drawing A6.102 and specification clause L20/410A and section L20 generally, and Aspex UK ironmongery and door schedule. All doors to be fitted into existing openings MUST have site measurements taken before manufacture. The door sizes indicated on the door schedule and door elevations are PROVISIONAL ONLY. |  |
| 3.5.2 | Riser Cupboard Doors Supply and install riser cupboard doors as per drawing A6.102 and specification clause L20/480A and section L20 generally, and Aspex UK ironmongery and door schedule. |  |
| 3.5.3 | New Dry Riser doors Supply and fix New Dry Riser doors to each landing – Stainless Steel Architrave & Door Outlet Cabinet L20/642 |  |
| 3.5.4 | Fire Rated Tiled Access Panels to Service Void in WCs |  |
|  | Supply and fix 450x450 60min fire-rated tiled access panel to service void in WCs. L20/630. |  |
| 3.5.5 | Non-Fire Rated Tiled Access Panels to boxing-in to cisterns and pipework to WCs |  |
|  | Supply and fix 450x450 tiled access panel to boxing-in to cisterns & pipework in WCs. L20/631. (1 each WC plus 1no. per washroom pipework). |  |
| 3.5.6 | Fire Rated Access Panels to Service Void in office space |  |
|  | Supply and fix 450x450 60min fire-rated metal door & picture frame access panel to service void in WCs. L20/632. |  |
| 3.5.7 | Fire Extinguishers |  |
|  | Supply and fix to each Floor CO2 & Foam extinguishers as N17/310/330 & fixed as N17/610. |  |
| 3.6 | Fittings |  |
| 3.6.1 | Window Blinds – Supply to all Business Units as N10/240. |  |
| 3.6.2 | Acoustic Panels – see pc sums |  |
| 3.7 | New openings & works at 6th floor to accommodate staircase access to new roof terrace |  |
|  | New opening roof slab and associated structural works in accordance with Structural Engineers details. New steel staircase with glazed handrail from 6th floor up to 7th floor (Roof Terrace) and new glazed enclosure A4.100 & A5.200 |  |
| 3.8.1 | Finish to Old Plant Room walls Dot and dab with adhesive, plasterboard and plaster skim coat the existing walls and ceiling to old plant room M20/280 Decorate as per Appendix M Include for a 100 x 25mm softwood skirting P20/ 111, painted M60/121 Include for new window cill to suit depth of P20/111. |  |
| 3.9 | New Suspended-ceiling to ground floor Entrance Corridor, Disabled WC, Shower Room & each Lift lobby landing and WCs |  |
| 3.10 | Form new drop-ceiling ground floor Entrance Corridor & to each upper floors’ Lift lobby landing & WCs as per K10/226A. |  |
| 3.11 | Consumer unit – cupboard doors & boxing-in to each unit. (PC sum) |  |
| 3.11 | Finishes |  |
| 3.11.1 | Bolon Flooring Provide and lay Bolon flooring to all floors in Entrance corridor Both Staircases Communal Landing areas Allow for DPM and 6mm plywood and latex screed to all floors and all cutting, waste etc. M50/111 |  |
| 3.11.2 | Vinyl sheet to Basement Booster Pump Provide and lay Vinyl sheet to Basement Booster Pump Room and Basement Comms. Room. Allow for latex screed and all cutting, waste etc. See drawing A1.109 and Specification ref: M50/150 |  |
| 3.11.3 | Matting to Ground Floor entrance: Gradus matting to fit within existing mat well. Remove external terrazzo externally within entrance canopy overhang. Form new mat well. Lay Gradus matting into new mat well. N10/300A |  |
| 3.11.4 | Tiling to all WC areas As shown on drawing A4.200 & M40/110 |  |
| 3.11.5 | Cost for re-skimming walls to make level for tiling. |  |
| 3.11.6.1 | Give cost for tiling cost/m2 |  |
| 3.12 | Spot Items |  |
| 3.12.1 | Fire stop armour cabling to rear of building as it enters adjacent café basement. Tie cable neatly back to wall. |  |
| 3.12.3 | Roof level existing edge protection- additional H&S requirements: Supply and affix to existing roof level edge protection where it is being retained – a 450mm high bar (20mm diam.) from finished roof level spanning from vertical upright to vertical upright to achieve current safety requirements. |  |
| 3.12.4 | Grab Rail to Lift motor Room Supply and fix a 450mm long grab rail to inner wall to lift room adjacent to door and steel access ladder. |  |
| 3.12.5 | Rear Lift Room Door Re-new and hang to opposite side rear lift room door. |  |
| 3.15 | General repairs/Maintenance |  |
| 3.15.1 | Carry out Repairs to roof & guttering of ground floor entrance canopy. |  |
| 3.15.2 | Flush out and rod through existing RWPs through building. |  |
| 3.15.3 | Flush out and rod through existing SVP through building. |  |
| 3.15.4 | Repairs to front elevation. Cut out and replace like with like 3no. glass blocks |  |
| 3.15.5 | Minor Repairs to front entrance canopy |  |
| 3.15.6 | Café Window Cills Cut out existing and renew café window cills along entire front elevation with new preservative treated timber. Decorate according to Akzo Noble Specification Appendix M. ‘Timbercare’ resin repairs to existing café window frames. |  |
| 3.15.7 | De-humidifier to be used in basement to reduce residual moisture due to over-flows (these are to be removed as part of the sanitary ware strip-out and up-grade). |  |
| 3.15.9 | Re-new timber fascia at low-level – first floor to each off-shot. Decorate according as Akzo Noble Specification Appendix M. |  |
|  | Mechanical and Electrical Works |  |
| 3.16 | Carry out all Mechanical and Electrical Services Works as contained in drawings and specification in Appendix D. |  |
|  | Structural Works |  |
| 3.17 | Carry out concrete repair work as per Structural Engineers drawings and specification contained in Appendix E. |  |
| 3.18 | All other works shown on drawings but not listed on this schedule. List all items. |  |
| 4.0 | Decorations |  |
|  | All paint finishes as per Azko Noble specification in Appendix M. |  |
| 4.1 | Emulsion paintwork |  |
|  | Prepare and apply one mist coat and two full coats of emulsion paint to walls, beams, columns, duct access doors & frames |  |
| 4.2 | Satinwood paintwork |  |
|  | Prepare and apply two undercoats and one top coat of satinwood paint to: all new timber surfaces All new exposed metal or plastic piping. Previously painted metal, wood and other surfaces Window cills Fixed wiring duct cover in ceiling to all units Perimeter Roof guards Café External grilles at basement level to café rear elevation |  |
| 4.3 | Diamond Eggshell |  |
|  | Terrazzo to staircase walls Staircase strings |  |
| 4.4 | Paintwork in WC ceiling |  |
|  | Prepare and decorate ceilings in WC as per specification clause. |  |
| 4.5 | Varnish to staircases’ handrails and to Café front elevation window frames, door etc.. |  |
| 4.6 | Paint external concrete entrance canopy |  |
| 4.7 | Varnish to parquet flooring to all business units M60/180A |  |
| 4.8 | All other surfaces described and specified in Appendix M but not listed here. |  |
| 5.0 | Roof Terrace & Access to Roof Terrace Works Carry out roof decking and balustrade works as per drawings: A4.101 A4.102 A4.103 A4.104 A4.105 A5.100 A5.101 |  |
| 5.1 | Staircase as to Roof Level |  |
|  | As per dwg A4.100. |  |
| 5.2 | Glass Enclosure to staircase to roof level |  |
|  | As per dwg A4.100 and A5.200 |  |
| 5.3 | Appendix I - Amalgamated Lift works quotation |  |
| 5.4 | 2 Paid Work Placements Contractor to provide 2 paid work placements – Refer to Employment and Training Code guidelines in Appendix J. |  |
| 6.0 | Works/products for/on behalf of the Employer |  |
|  | Ref: project preliminaries A50/110a, 110b & 110c. |  |
|  | Allow for management and co-ordination of the works of the following directly appointed contractors/suppliers, so that these works are contained within the contractor’s master programme: |  |
|  | Security and CCTV (Chubb) works contained in Appendix M |  |
|  | Fire (T&P Fire) contained in Appendix N |  |
|  | Cabling Works, ICOM– Appendix O (part to follow) |  |
| 7.0 | Section 6 - Provisional sums |  |
|  | Staircase to Roof Level | 42,000 |
|  | Alterations to WC drainage | 2000 |
|  | New slab to infill loft access hatch | 500 |
|  | Asbestos removal (if found) | 20,000 |
|  | Pigeon Guano removal (internally) | 3000 |
|  | Internal display signs and boards incl. fire signage | 3000 |
|  | Graphics to landing walls Digital Wallpaper From artwork supplied. 2 walls 9m W x 3m H Including priming of walls and installation Old Street. | 3000 |
|  | Acoustic Panels | 100,000 |
|  | Light-boxes Tension fabric system complete with graphic. Please note this is based on each light-box having an external driver. 14 light-boxes 250mm x 250mm Including installation Old Street | 3000 |
|  | External sign | 1000 |
|  | Roof repairs | 1000 |
|  | Lightening protection | 15,000 |
|  | Plastering – Stipulate Rate (£) per m2 |  |
|  | PC sum for plastering |  |
|  | Repointing to external concrete cills – Give Rate per m2 | Rate - |
|  | PC sum for repointing to external concrete cills. |  |
|  | Concrete Repair – Give Rate per m2 | Rate - |
|  | PC sum for concrete repair |  |
|  | Post completion fittings | 2000 |
|  | Bike Storage sheds BWIC | 5000 |
|  | Install swing gate to rear access road including mass conc. foundations | 10,000 |
|  | Contingency | 25,000 |
|  | Other general repairs | 20,000 |
|  | Boxing in to 13 no. new comms. cabinets within each business unit | 6000 |
|  | Joinery in connection with cabinet to letterbox | 500 |
|  | Joinery in connection with glazed-fronted cabinet to fire Panel | 500 |
|  | Rear External Door 2 (Fire Escape) ironmongery | 1000 |
|  | Rear External Door 3 ironmongery | 1000 |
|  | Rear External Door 4 (to Look Mum No Hands) ironmongery | 1000 |
|  | Rear External Door 5 to Basement commercial unit ironmongery | 1000 |
|  | External Door No.4 at Roof Level | 1500 |
|  | Fill in loft hatch with steel filler joists and concrete | 2000 |
|  | 3 no. hardwood treated timber packers & HW treated cills to give a minimum 150mm upstand | 500 |
|  | Re-locate roof aerial | 500 |
|  | Remove areas of existing plasterboard ceiling to 13 no. Business Units to locate secure fixing points to ceiling slab for 4 no. Air Con units - per Business Units – make good. | 13,000 |
|  | Adjustments to edge protection at seventh floor roof level | 1000 |
|  | Visual & acoustic barriers to 4no. roof mounted mechanical air con plant | 2000 |
|  | New acoustic panels to business units | 25,000 |
|  | Total carried to form of tender |  |