Bath Western Riverside,  Bridge Demolition Works over River Avon.

Bath & North East Somerset Council give prior notification of the issue of a tender enquiry package for bridge demolitions works.

The bridge demolition works concern two, soon to be redundant,  gas infrastructure bridges which span the River Avon in Bath, South West England and are located as follows:

* West Gas Pipe Bridge  51.384039,  -2.381415
* East Gas Pipe Bridge 51.384596, -2.379491

As part of this PIN the Council wishes to engage with specialist contractors with the resource and expertise in bridge demolition works in constrained site environments to understand the contractor perspective regarding the works.

You may contact : [jeff\_owen@bathes.gov.uk](mailto:jeff_owen@bathes.gov.uk) to discuss this tender opportunity.

The Contract Notice containing a Restricted Tender procedure is anticipated to be issued in early November 2021 following the procurement timetable outlined below.

**Procurement Timetable / Programme:**

|  |  |  |
| --- | --- | --- |
| Task Name | Start | Finish |
| PIN | July 21 | Oct 21 |
| Contract Notice & Tender Package Published | Nov 21 | Dec 21 |
| Selection Questionnaire Received | Dec 21 | Dec 21 |
| Selection Questionnaire Evaluated & Shortlisted | Dec 21 | Jan 22 |
| Invitation to Tender Issued to shortlisted contractors | Jan 22 | Feb 22 |
| Tender closing date | Feb 22 | Feb 22 |
| Tender clarification/evaluation | Feb 22 | March 22 |
| Contract award & standstill period | April 22 | April 22 |
| Contractor appointed | May 22 | May 22 |
| Demolition Works | Oct 22 | March 23 |