BLACKPOOL BOROUGH COUNCIL

and

[CONTRACTOR]

YEADON WAY PHASE 2 PROJECT

|  | CONTRACT DATA PART ONE DATA PROVIDED BY THE EMPLOYER |  |
| --- | --- | --- |

# GENERAL

## The conditions of contract are the core clauses and the clauses for Option A, dispute resolution Option W2 and secondary Options X7, [X13], X15 and X16 together with Addendum Y(UK)2(as amended by the z-clauses) and Addendum Y(UK) 3 of the NEC Engineering and Construction Contract (April 2013) ("Contract").

The works are the design, construction, testing and commissioning works for the Phase 2 Remediation of Yeadon Way, Blackpool as set out in the Works Information, including Replacement of road pavement, road drainage and street furniture, Embankment remediation works to satisfy a betterment performance criteria: to enable the replacement road pavement to achieve a minimum 15 year period without repair/maintenance following completion of the works.

## The Employer is:

Blackpool Borough Council 
PO Box 11
Town Hall
Blackpool Lancashire
FY1 1NB

## The Project Manager is:

Steven Gilmour
Blackpool Borough Council
No. 1 Bickerstaffe Sq.
Talbot Road
Blackpool
Lancashire
FY1 3AH

## The Supervisor is:

Robert Sutcliffe 
Blackpool Borough Council
No. 1 Bickerstaffe Sq.
Talbot Road
Blackpool
Lancashire
FY1 3AH

## The Adjudicator is:

The Adjudicator shall be the person agreed by the parties or chosen in accordance with the information contained within the Optional Statements below.

## The Principal Designer is

## Raydar Safety Limited

## Merchant House

## Corn Exchange

## Rawtenstall

## Rossendale

## BB4 8EU

## The Works Information is in the document entitled "Works Information" appended to the memorandum of agreement between the Employer and the Contractor.

## The Site Information is provided in or referred to in the Works Information.

## The boundaries of the site are set out in the Works Information and are shown on drawings numbers 03079AB/001-1 Rev A, 03079AB/001-2 Rev A and 493272.T.003

## The language of this contract is English.

## The law of the contract is the laws of England and Wales, subject to the jurisdiction of the courts of England and Wales.

## The period for reply is two weeks.

## The Adjudicator nominating body is the President of the Institution of Civil Engineers.

## The tribunal is the Courts of England and Wales.

# time

## The starting date is the 11th November 2019

## The Contractor submits revised programmes at intervals no longer than five weeks.

# testing and defects

## The defects date is 52 weeks after Completion of the whole of the works.

## The defects correction period is four weeks unless it affects the safety of people, personnel, property and/ or the safe use of the highway in any way, in which case it requires immediate attention.

# payment

## The currency of this contract is pounds sterling (£).

## The assessment interval is monthly.

## The interest rate is 2% per annum above the average base rate of the Bank of England.

# compensation events

Not applicable

# risks and insurance

## The minimum limit of indemnity for insurance in respect of loss of or damage to property (except the works, Plant and Materials and Equipment) and liability for bodily injury to or death of a person (not an employee of the Contractor) caused by activity in connection with this contract for any one event is £10,000,000.00.

## The minimum limit of indemnity for insurance in respect of death of or bodily injury to employees of the Contractor arising out of and in the course of their employment in connection with this contract for any one event is £10,000,000.00.

# Optional Statements

## The completion date for the whole of the works is 22nd May 2020.

## The Contractor is to submit a first programme for acceptance within two weeks of the Contract Date.

## Delay damages for the works is £1236.00 per day including Saturday and Sunday

## The assessment interval is one calendar month for every subsequent month after the first agreed assessment date

## The period for payment is set out in clauses 50, 51 and Y(UK)2 except the period in Y(UK)2.2 is 21 days after the payment becomes due

## The retention free amount is nil.

## The retention percentage is 5%.

## The amount of the performance bond is 10% of the total of the Prices.

## The additional conditions of contract are those attached to the memorandum of agreement between the Employer and the Contractor.