# FORM OF TENDER

### SYDNEY HOUSE CAR PARK, TORRINGTON –

### RESURFACING WORKS.

TO:	The Chairperson and Members of the Torridge District Council

Sirs,

We, the undersigned, having read the Conditions of Contract and Specification/Schedule of Works and having examined the drawings and other documents referred to therein, do hereby offer to execute and complete, in accordance with the Conditions of Contract, the whole of the works described, for the fixed price sum (excluding V.A.T.) of :-

£

(IN WORDS)  :

................................................................................................................................................

We undertake to commence the Works 2 weeks from the date of acceptance of tender and complete the whole of the Works within 6 weeks from the date of possession.

We agree that should obvious errors in pricing or errors in arithmetic be discovered before acceptance of this offer, in the priced schedule of works, we must confirm or withdraw the offer in accordance with the principles of the Construction Industry Board “Code of Practice for the selection of Main Contractors”, clause 4.7 with overall price dominant.

This tender will remain firm and open for consideration for 8 weeks from the date fixed for the submission of tenders.

Other than for insurance purposes, we confirm that we will not divulge the tender figure prior to the deadline for submission.

Dated

Name:		     	                                              Telephone No.:

Company:

Address:

Name:

Witness:

## APPENDIX

Form of Contract: 				JCT Minor Works

2.1		Date of Possession:				2 Weeks from acceptance of tender

2.3		Liquidated and ascertained damages:		£520 per week or part thereof

4.2		Period of Interim Certificate:			Monthly

Period for payment of Certificate:		30 days

Percentage of Certified value retained:		5 %

4.3		Percentage of Penultimate Certificate retained:	2.5 %

4.4		Period of final measurement and valuation:	3 months from Practical Completion

6.3		Insurance - Public Liability:			£5,000,000