## **Schedule 1 (b) Invest in Youth**

## **Project numbers; Outputs, results and Soft Outcomes.**

|  |  |  |  |
| --- | --- | --- | --- |
| Target from project outline | Invest in Youth Outputs | Milestones | Timescale |
| People engaged in work readiness activities of which: | 770 | 200385185 | July 2017July 2018July 2019 |
| Men | 385 | 10019392 | July 2017July 2018July 2019 |
| Women | 385 | 10019392 | July 2017July 2018July 2019 |
| Unemployed | 385 | 10019392 | July 2017July 2018July 2019 |
| economically inactive | 385 | 10019392 | July 2017July 2018July 2019 |
| people with disabilities | 155 | 417539 | July 2017July 2018July 2019 |
| ethnic minorities | 75 | 203817 | July 2017July 2018July 2019 |
| People moving into education or training  | 100 (13%) | 135037 | July 2017July 2018July 2019 |
| People moving into employment or self-employment  | 100 (13%) | 135037 | July 2017July 2018July 2019 |
| People who were economically inactive moving into job search | 208 (27%) | 2710477 | July 2017July 2018July 2019 |

|  |  |
| --- | --- |
| **Project Outcome** |  |
| **Individuals will demonstrate an increased level of engagement with support services or potential employers** | * 150 participants will access health and wellbeing provisions such as (GP, dentist, substance misuse support)
 |
| * 400 minimum hardest-to-reach participants will maintain meaningful engagement with Invest in Youth support providers
 |
| * 250 minimum participants will attend an interview for employment or training
 |
| **Participants will identify skill gaps and increase skills** | * 100 minimum participants will identify learning that is necessary for them to overcome their skill gaps as part of their Action Plan
 |
| * 200 minimum participants will learn the skills they need in order to create or update their CV
 |
| * 400 minimum participants will improve their basic, digital, financial or personal skills
 |
| **Individual participants will feel more empowered, motivated and confident to take decisions about their own lives that will lead to improved wellbeing** | * 150 minimum participants will say their confidence has increased
 |
| * 150 participants will feel more positive about their future and will be able to understand aspirations and identify their own
 |
| * 150 participants will feel that their needs have been listened to and that they have a clear plan for change
 |
| **Individuals with a responsibility for caring for others (children or family members) will have greater capacity and confidence to take time away from caring to look after their own needs** | * 30 minimum participants with caring responsibilities will have increased knowledge of their childcare/respite care options in preparation for getting back to work
 |
| * 30 minimum participants will feel more confident that they would be able to manage the demands of caring and working
 |
| * 6 participants with caring responsibilities will move into employment
 |