2018 – 2022 Property Professional Services Framework (2018/S 005-007230)

Further Competition Invitation to Tender (Stage 1 Under FTS Threshold)  REVISED ITT DOCUMENT

South West Rugby – Property Advisory and Agency  Services

Issue Date: 23/08/2022

ProContract Identification Number: DN629603

Table of Contents

Part 1 - Commission Requirements	4

1.	Commission Background	4

1.1	Strategic Context	4

1.2	South West Rugby SUE	5

1.2.1	Site/ background	5

1.2.2	Planning Status	6

1.2.3	Homes England Key Objectives	7

1.3	Homes England role at SW Rugby SUE	8

1.4	Consultant Appointments	12

2.	The Services	13

3.	Indicative Programme	23

4.	Management	23

4.1	Homes England Personnel	23

4.2	Other Personnel	24

4.3	Meeting Requirements	24

4.4	Invoicing	25

5.	Other Requirements	25

5.1	Termination	25

5.2	Conflict of Interest	25

5.3	Confidentiality	25

5.4	Future changes to scope of works	26

5.5	Framework Contract	26

Part 2 - Instructions for Submitting a Response	27

1	General	27

2	Quality	28

3	Pricing	28

4	Evaluation	30

5	Documents to be Returned	30

6	Procurement Timetable	31

7	Evaluation Criteria	32

8	Worked Example	38

Part 3 Response Form	40

Appendix A DPS Technical Pack Checklist	43

Introduction

The purpose of this Further Competition Invitation to Tender (ITT) is to award the call-off contract for the above commission.

We ask you to respond to the questions detailed in Part 2, Section 6 (Evaluation Criteria) using the Response Form and to return the Response Form and Resource and Pricing Schedule in Part 3 with your tender.

This Further Competition ITT is divided into 3 parts:

Part 1 – Commission Requirement

- Details the commission requirements.

- Details additional terms and conditions for the Further Competition.  The successful Supplier will be subject to both the terms and conditions of this Further Competition and the Framework Contract.  Unless otherwise defined in these instructions, terms used shall have the meaning given to them in the Framework Contract.

Part 2 – Instructions for Submitting a Response

- Contains important information and instructions on preparing and submitting a tender response.  Please read these instructions carefully prior to submitting your tender response.

- Outlines the evaluation criteria which will be used for assessment.  It is important that Suppliers familiarise themselves with the criteria and ensure they are considered when compiling their tender response.

Part 3 – Standard Forms

- Contains the standard forms required to be completed and returned by the Supplier when submitting a tender response.

# Part 1 - Commission Requirements

# Commission Background

# Strategic Context

- Homes England set out a five-year strategic plan in 2018:

https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/752686/Homes_England_Strategic_Plan_AW_REV_150dpi_REV.pdf

- In line with our organisational strategic objectives, we have a mandate to:

- Provide expert support for priority locations, helping to create and deliver more ambitious plans to get more homes built.

- Promote better design and higher quality places.

- Understand the need and opportunity for investment in land, infrastructure to unlock the market and support affordability of housing.

- As part of the Agency’s 5-year plan, several significant acquisitions of large-scale stalled sites have been made, with a range of Agency interventions available to enable the progression of these sites including direct investment, a master developer role, site-enabling and the provision of other support. The acquisition of circa 92 ha of land capable of delivering over 1,500 homes at South West Rugby Sustainable Urban Extension (SUE) represents one of these recent acquisitions (March 2020).

- Homes England seeks to appoint a property/development consultant to provide ongoing strategic and detailed property advice for the project and to work with Homes England and its consultant team during the preparation of outline application(s) for residential-led, mixed-use development on the site to ensure any planning permissions are market facing and viable. The property/development consultant will be required to advise on the disposal strategy for the Homes England landholdings once outline planning permission has been granted, including supporting Homes England in its role as a consortium member, and will lead on site marketing for Phase 1 land Parcel HE1a and HE1b via the Homes England Dynamic Purchasing System (DPS).

- Homes England has a commitment to maintaining high quality throughout the design and delivery process through to disposal and requires the property/development consultant to work closely with the wider Homes England consultant team to ensure that this is promoted in a consistent manner across all workstreams.

- Homes England anticipates that bidders will put forward a bespoke team of leading practitioners to meet the specific requirements of this brief.

- The appointment of a property agent to advise on the disposal of later phases of Homes England land interests will be undertaken as a separate appointment via a new tendering exercise at the appropriate time, although Homes England reserves the right to amend and / or extend the scope of this commission including adding additional phases of its land.

# South West Rugby SUE

# Site/ background

- South West Rugby SUE is a strategic allocation in the adopted Rugby Borough Council (RBC) Local Plan (2019), and is set to deliver circa 5,000 new homes, primary and secondary schools, a new neighbourhood centre, 35 ha of employment land and green and blue infrastructure, in addition to key highways infrastructure that will bring improvements to the wider South West Rugby area.

- The site’s allocation includes the requirement for a new link road (the Homestead Link) to alleviate congestion on the nearby village of Dunchurch.  The allocation site is identified on the plan at Figure 1 below:

Figure 1 -South West Rugby allocation boundary

- Comprehensive development has stalled due to a range of factors including significant upfront infrastructure requirements, the complexities of an agreed mechanism to recover the costs of enabling infrastructure and the involvement of multiple landowners/promoters.

- The requirement to deliver enabling infrastructure has been identified as key to unlocking the delivery of new homes at this site, including most notably the Homestead Link Road.  To unlock development, in 2020 Homes England acquired 63.06 ha of land from Warwickshire County Council (WCC), and 29 ha of land from private ownership (M Deeley Land), totalling 92.06 ha.  Homes England has adopted the role of Master Developer and has secured funding from the Treasury that includes forward funding of strategic highways including the Homestead Link Road, strategic utilities and community infrastructure.

- This funding is conditional on the need for the scheme to be ‘an investable proposition’ and for suitable mechanisms to be put in place for Homes England (and Treasury) to recover its investment. This includes the need for an all-party collaboration agreement, site wide masterplan, viability assessment, and infrastructure delivery plan.

- Homes England has worked closely with the multiple landowners and has formed a consortium with Taylor Wimpey, L&Q Estates and Richborough Estates.  In addition, the consortium is working with Tritax Symmetry on the delivery of utilities on the site.

- The ownership / promotion boundaries of the site are identified on the plan at Figure 2 below.  Please note the land marked as Owen & Haywood is now in Homes England ownership

Figure 2 -South West Rugby land ownership

# Planning Status

- The Council adopted the South West Rugby SPD in June 2021 to guide development on the site. The key policy objectives from both DS8 and DS9 are key threads to the SPD.

- Policy DS8 SPD allocates South West Rugby to provide around 5,000 dwellings and 35 ha of employment land for B8 uses, and clearly states that the Council will not support ad hoc or piecemeal development. The SPD also includes a Masterplan that sets out the Council’s preferred locations for open space, access, play areas, the school or schools, primary roads and other features.

- Policy DS9 allocates land to facilitate the full alignment of the South West Rugby spine road network to support and enable the South West Rugby allocation to be developed comprehensively.

- Two parts of the allocation already benefit from planning permission, the locations of which are identified by the yellow stripes on the plan at Figure 1. These are:

- An outline application for up to 860 homes and a new primary school was granted at Appeal in July 2017 (LPA Ref: R13/2102). The application was submitted by L&Q Estates (then Gallagher Estates). Reserved matters have been submitted and development has commenced on site.

- An outline application for 150 homes was approved in January 2018 (LPA Ref: R15/1816). The application was submitted by Miller Homes. Reserved matters have been approved the development is largely complete.

- The remainder of the site is being progressed by numerous other private landowners and promoters (Taylor Wimpey, Tritax Symmetry, L&Q Estates and Richborough Estates) and by Homes England.

- Despite the need for the site to be delivered in a comprehensive manner, a number of early applications have been submitted within the allocation. These include:

- An outline application for 186,500 sqm of B8 floorspace submitted by Tritax Symmetry secured a resolution to grant planning permission subject to the completion of a s106 at planning committee on 16 September 2020 (LPA Ref: R16/2569). The s106 was completed and the decision notice issued in November 2020.

- Tritax has since submitted an application for full details of the first two B8 units at the southern entrance to the site (LPA Ref: R20/1026) which has now been approved and several other reserved matters applications relating to different phases of the scheme have been submitted and are being considered by the Council.

- An outline application for 210 homes and a new primary school submitted by L&Q and validated in March 2019 (LPA Ref: R18/0936). The application was considered at planning committee in March 2021 where members resolved to approve the application subject to the completion of a s106 agreement. The decision notice has not yet been issued as the s106 agreement has not yet been agreed.

- An outline application for 275 homes submitted by Tritax Symmetry and validated in May 2019 (Ref: R18/0995). The application is still being considered by the Council.

- In addition, Homes England is currently preparing a planning application for the Homestead Link Road and is targeting submission in mid-2022. An outline application for Homes England first residential and mixed-use phases is being targeted for submission in late 2022/early 2023.

# Homes England Key Objectives

- Homes England’s key objectives for the wider project include (but are not limited to):

- Securing the delivery of better homes, faster, at South West Rugby.

- Ensuring high quality Place Making principles are adhered to.

- Drive value for money and efficiencies in project delivery.

- Lead an ambitious and commercial approach to the delivery of SW Rugby.

- Collaboration and partnership working to be inherent throughout the project delivery process.

- Ensure accurate programme management giving confidence to the Homes England’s sponsor department and project partners.

- Compliance with Homes England’s approvals and funding conditions (to be provided to the successful supplier).

- Compliance with all legal and statutory obligations applicable to the delivery of the project during the duration of the appointment.

- Homes England is also working with Warwickshire County Council and Rugby Borough Council in developing a set of shared objectives, which will include addressing the declared Climate Change emergency.

# Homes England role at SW Rugby SUE

- Homes England has a dual role at SW Rugby SUE which is reflected in the requirement in this commission.  As landowner, Homes England is seeking to maximise housing delivery and supporting community uses on the 92.06 ha of land in its ownership.

- In its role as Master Developer, Homes England is forward funding and leading on the delivery of key highway and utility infrastructure, and the preparation of a Site Wide Masterplan and Strategic Infrastructure Delivery Plan that provides a basis for the phasing of the project. The plan at Figure 3 below shows the indicative phasing plan, with Homes England phasing shown by plots HE1 to HE5.  Please note the parcel marked O&H1 is now in Homes England ownership and will be included within Phase 1 land as parcel HE1e.

Figure 3 -South West Rugby development parcels

- An initial approach to phasing principles for the Homes England land holdings has been developed, with the critical early phases comprising the Local Centre site and associated residential phases, shown in red on the aerial at Figure 4 below, with future phases as shown in orange. Proposals for the Local Centre need to be developed which incorporate a mix of uses including schools, retail / commercial, community buildings, potential Co-Mobility Hub, care home / extra care / sheltered housing, Safer Neighbourhood Policing.

- It is currently anticipated that the Homes England land will be subject to three outline planning applications, albeit this has not been confirmed and is subject to change:

OPA 1 – Land in the red line boundary, comprising HE1 and HE2, as well as the recently acquired Owen and Haywood land, will form the first outline planning application

OPA2 – ‘Southern land’ comprising He3 and HE4a

OPA3 – ‘Deeley land’ comprising HE4b and HE5

- There may also be a requirement to extend the extent of the outline permission to land outside Homes England land ownership.  Your methodology should reference this requirement for flexibility although there is no requirement to provide a fee proposal for an extended OPA boundary at this stage.

Figure 4- South West Rugby initial phasing plan

- The current phasing assumptions (subject to refinement with the Property Consultant) are as follows:

Phase 1 land - Land in red line boundary (Figure 4) – also refer to figure 3 for parcel detail

- The land in the red line boundary includes the earlier phases of development, including the District Centre and associated healthcare and education facilities:

- HE1a – Parcel of land identified for potential delivery of up to circa 263 units between 2025/26 and 2026/27. Parcel HE1a will be split into two parcels subject to two separate disposals through DPS, currently anticipated to be as follows:

  - SME - Anticipated a parcel will be delivered targeting SMEs to deliver circa 73 standard housing units between 2025/26 and 2026/27.

  - PRS - It is currently envisaged that this plot would be suitable for the delivery of circa 190 PRS units between 2025/26 and 2026/27 to diversify residential typologies and to prevent over supply of market housing across the wider SWR SUE site.

- HE1b - Parcel of land identified for potential delivery of up to circa 170 residential units between 2028/29 and 2031/32.   This parcel of land is currently anticipated to be split into two parcels as follows:

  - Negotiated disposal - there is potential for negotiated disposal of part of this site to one of the consortium members to create a more regular development parcel, this will accommodate approximately 70 units. We will require general property advice and valuation services in respect of this, to include advice on a negotiated disposal and Red Book valuation to support the transaction. Please note further detail in Scope of Services below.

  - Remaining Homes England land - The land that will remain in Homes England ownership is anticipated to deliver 100 residential units between 2026/27 and 2028/29.  Homes England has aspirations to increase delivery of MMC and this site could provide an opportunity for this.

- HE1c – This is the parcel of land identified for the all-through school and community sports pitches to be transferred to WCC. Delivery timescales are to be confirmed, and these parcels will ultimately be transferred to WCC in due course.

- HE1d – Central to the project area, this parcel is expected to be a mixed-use development comprising local centre with retail and community services including health care hub, as well as some residential. The delivery of this parcel is expected to be phased, and timescales for delivery are to be confirmed and dependent partly on healthcare requirements.   Please note ‘Services’ below that set out a requirement for some focussed work on developing the right balance of uses for this element of the scheme to ensure the best provision in terms of services and amenity (Stage 1b).

- HE1e – Referred to on plans as Owen and Haywood land, this parcel of land has recently been acquired by Homes England and is capable of delivery of circa 53 residential units between 2025/26 and 2026/27.

- HE2 – Being adjacent to the local centre, this parcel provides potential for a mix of standard housing and retirement living totalling circa 215 units, timescales will be dependent upon delivery of HE1c and HE1d but we anticipate delivery will commence in 2026/27. Current assumptions are that this parcel will be disposed of in two parcels each subject to a separate disposal process through DPS.

Phase 2 land - Land in orange line boundary (Figure 4)

- The land in the orange line comprises the ‘southern land’ (HE3 and HE4a) and the ‘Deeley land’ (HE5 and HE4b).

- HE3 – Site identified as a possible location for the development of circa 127 residential units using Modern Construction Methods (MMC) between 2026-27 and 2028-29.  This site could potentially be used to target SME developers but this will be refined as part of the disposal strategy subject to market testing.

- HE4a– Development of circa 298 residential units between 2030-31 and 2034/35. It is currently envisaged that part of this site could be targeted to SME developers, with a disposal of a parcel capable of delivering 50 residential units being subject to its own disposal process. The remaining land would be capable of delivering 248 residential units to be split into two separate disposal processes.

- HE4b and HE5 – Development of circa 525 residential units between 2031/32 and 2036/37.

- Custom Build/ Self Build - (HE4a and HE3) There is potential for early delivery of Custom Build/Self Build plots (possibly part of the ‘Dunchurch parcel’ (HE4a and HE3) subject to market advice) and the overall masterplan should consider options for this.  Please note Stage 1c work set out in The Services below.  There will also be an option to extend the commission to manage a Custom/Self Build/SME disposal. Your fee proposal should include this disposal. Please assume four DPS disposal processes, with HE3 being sold in single disposal process and He4a being subject to three separate DPS disposal processes. Please note table 1 below at page 21 for further guidance on likely sales values.

- The above remains subject to refinement and advice on site parcelling and phasing of the Homes England land holdings and forms a key part of this commission.

Draft disposal strategy

- The development of a robust disposal strategy for Homes England land that is compliant with the Homes England Land Disposals Policy is a key workstream for this commission. The current draft disposal strategy for the South West Rugby SUE is focussed on delivering a range of housing products across different tenures and property type to accelerate overall housing delivery across the SUE. The successful consultant will be required to advise on appropriate site parcelling to attract a range of developer types including national/ regional housebuilders, SMEs, custom/ self-build and to deliver a range of property types and tenures to create a varied and long-lasting community and sense of place.

- Homes England expects, given the varied nature of housing typologies to be delivered on Homes England land, that it would be disposing of multiple parcels of land to different delivery partners at the same time in order to expedite delivery. The nature and speed of these disposals will be developed in a balanced and sustainable way, complimentary to the needs of the wider development.

- Homes England has stated an objective to bring in private sector expertise at the earliest possible stage, which will have a direct impact upon timescales for plot sales.  Homes England will dispose of parcels of land via the Dynamic Purchasing System (DPS), or subsequent framework, using the Council’s adopted SPD, the planning application process, and the articles of the Consortium agreements (where relevant) to build these requirements and ambitions into the scoring and selection criteria to ensure it achieves the best value and outcomes for its land.

# Consultant Appointments

- Homes England has appointed a consultant team to support the planning application for the Homestead Link Road and landscape buffer, preparation of the site wide masterplan, and wider site strategies for utilities, drainage, and earthworks.  The appointed team and a summary of their roles is provided below:

- Arcadis - Highways Designer: appointed to progress the design for the Homestead Link Road planning application, progress technical approvals and support the delivery of the link road. This instruction has been extended to include support on the procurement of an IDNO for utilities, and preparation of site wide earthworks and drainage strategies.

For the avoidance of doubt, Arcadis will continue to oversee all work streams on behalf of Homes England with the overall project management lead in respect of SW Rugby.  All other consultants listed under paragraph 1.4 will be subject to Arcadis Project Lead directions although they will be directly appointed by Homes England under the relevant Framework Panel arrangements.

- Arcadis - Project Manager and Cost Consultant: 3-year appointment from April 2021 to deliver the over-arching project management role for homes England. Key responsibilities include the preparation and management of: Project Execution Plan; Master programme; cost management strategy; risk register; overarching responsibility matrix; communication strategy; document control; estate management updates; principal designer/ CDM; and site wide long-term stewardship. This has included the identification of site constraints and opportunities, with costed mitigation strategies and solutions, and to inform viability modelling and development appraisal work.

- Wood - Multi-disciplinary consultant: Wood is appointed by Homes England to work alongside Arcadis’ highways designer to prepare the planning application for the Homestead Link Road including the Environmental Impact Assessment and Environmental Statement.

- Wood – Ecology: Appointed to advise Homes England on its landholding including all ecological survey work, Biodiversity Net Gain (BNG), and will prepare the ecology supporting documentation for the outline planning applications (including ecology EIA chapters).

- The Environment Partnership (TEP) - Landscape design and arboriculture: appointed to prepare the landscape scheme and tree survey information for the Homestead Link Road planning application.

- AFL Architects - Masterplanning: appointed to prepare the site wide framework masterplan and design principles for the wider SUE.

- Savills - property consultancy support: in respect of work undertaken to date including market reports, site wide viability, retail and leisure advice, Part 1 claims.   This instruction has now ended and will be replaced by the appointment subject to this tendering exercise.

- All relevant technical information will be made available to the successful consultant.

- Homes England is also seeking to appoint a team of advisors to support our role as landowner to ensure the value and deliverability of our own landholdings is maximised.  As well as this property/development consultancy appointment, we are also looking to make the following key appointments to support the Agency in the preparation of outline planning application(s):

- Masterplanning: to work with the appointed consultant team to build upon the framework masterplan and develop an indicative masterplan(s) for Homes England’s land to form part of outline applications and preparation of site-specific Design Code/ Plot Passports.

- Multi-Disciplinary:  A consultant from the multi-disciplinary panel to provide technical support and advice, and to prepare the supporting documentation (including an EIA and ES) as part of outline planning applications.

- Property Agency / Disposals - The appointment of a property agent to advise on the disposal of later Homes England phases via the Dynamic Purchasing System (DPS) will be undertaken as a new tendering exercise at the appropriate time.

- The successful property consultant will be required to work closely with the appointed consultant team but particularly the masterplanner to ensure that Homes England objectives are promoted in a consistent manner across all workstreams.

# The Services

- The purpose of this Competition Invitation to Tender (ITT) is to appoint a property advisor to provide support to Homes England during the preparation of outline planning application(s) for residential-led, mixed use development on the site, ensuring those permissions are market facing and viable. The consultant will also advise Homes England in the development of a robust disposal strategy for its land ownership at SW Rugby SUE, including supporting Homes England in its role as a consortium member, and to lead on the disposal of Phase 1 land Parcel HE1a and HE1b via the Homes England Dynamic Purchasing System (DPS).  We also request a fee proposal for disposal of Phase 2 plots HE3 and HE4a only, and reserve the ability to instruct on this disposal in the future. This will be subject to performance and fee levels remaining within the OJEU threshold.

- The contract is anticipated to run for an initial period of 3 years, with the option to extend by a further 2 years in increments of 1 year, a total potential contract duration of 5 years. Please note, the fee proposal is to be based on outputs as per the resource and pricing schedule outlined below.

- Based on the above, Homes England will require the appointed agent to undertake the key services listed below. This is not an exhaustive list and the consultant is requested to make any recommendations for amendments or additions in their return. Please note, we reserve the right to amend the scope of services to meet the requirements as the project progresses. This may result in the earlier phases exceeding agreed fee levels that could result in some of the later phases having to be removed from the commission, for example.  Please refer to Section 5.4 for further information.

- Suppliers should provide an approach and fee quote for each element of Stages 1 to 7 of The Services listed below.  PLEASE NOTE: There is a Resource & Pricing Schedule attached.  The Schedule lists out the services set out below (Stages 1 – 7). This table is to be completed for the purposes of the Financial bid, and will also be scored for responding to the qualitative elements of the bid including appropriate allocation of resource.

- Services under stages 1 to 3 are required for all Homes England landholdings, and stages 4 – 7 for Phase 1 land only (OPA1, red line boundary, Plot HE1a and HE1b only) and a fee proposal for disposal of Phase 2 land (part of OPA2 orange line boundary, Plot HE3 and HE4a) is also required.

Stage 1 – Masterplan Development

Stage 2 - Masterplan Testing and Refinement (including development viability)

Stage 3 – General Property Advice on Disposal Strategy for Homes England land

Stage 4 – Site Marketing Preparation via DPS

Stage 5 – Site Marketing and Disposal via DPS

Stage 6 – Legal negotiations to Contract Award

Stage 7 – Post contract monitoring

- Please see below a full breakdown of each stage of work with a relevant set of delivery outputs.

Stage 1 – Masterplan Development  (split into 3 workstreams as follows:)

Stage 1a. Masterplan Development - General

- Review the Framework Masterplan and Visioning/ development work produced to date and provide initial high-level views on strengths and weaknesses, areas for improvement and any opportunities that can be incorporated.

- Carry out a property market review to support masterplan development process, including advice on values, phasing, tenure, affordable housing mix and potential grant funding options, development mix, market attractiveness, Homes England objectives, etc. This should be presented in a market report summarising market advice.

- Working collaboratively and iteratively with the appointed masterplanning consultant during the planning application process, and using the existing Framework Masterplan, Vision and Principles as the basis, provide commercial input to support the development of an evidence based, commercially successful/ viable and market facing masterplan and supporting design code / plot passports that maximise the value and housing potential of the site.  These should also maximise achievement of key Homes England policy objectives around MMC, SMEs, self-build, affordable housing mix, BNG, Future Homes Standard etc.

- Review the draft site wide phasing plan prepared to date and provide advice on how this could be improved/ amended for Homes England landholdings whilst retaining the overarching delivery strategy for site wide infrastructure and the need for diversity in tenure and product so multiple phases across the SUE can be delivered concurrently.

Please note, the draft phasing plan and product / tenure types are indicative only and the assumptions underpinning the phasing plan should be tested throughout the masterplanning process in collaboration with the wider consultant and client team.

Stage 1a. Delivery Outputs:

- Market report for all masterplan uses.

- Commercial input into viability and marketability of the housing offer proposed by the masterplan options produced by masterplanner.

- Input into the phasing plan for Homes England land holdings (to be prepared by the appointed masterplanner).

Stage 1b. Masterplan Development – District Centre

There is a requirement for a dedicated workstream to work up in detail the right mix of uses and unit sizes for the District Centre, including supporting the requirements for the outline planning application. The District Centre is to be delivered on land within Homes England ownership and this provides the opportunity to steer the form of development and provide a District Centre that meets the needs of both existing and new communities that will be served by this development. This will include suitable retail, leisure and supporting community uses, including a 3-7 GP surgery / healthcare hub as required by planning policy. The District Centre could include residential uses on the upper floors or as standalone blocks within the centre and could incorporate senior living and care accommodation, subject to market demand and advice. It is essential that this work is informed by market testing with developers, operators and occupiers.

The extent and layout of the District Centre is critical as this will dictate the alignment of key highway infrastructure including works to Cawston Lane and the delivery of a Community Spine Road.

It is anticipated that the education and health facilities can be used as an early phase of the District Centre development to help drive footfall and vibrancy, possibly with an early phase / block of retail.  Homes England, working with Warwickshire County Council and Coventry and Warwickshire Care Commissioning Group (CGG), will provide the specification and phasing for the education and health facilities. The consultant should undertake additional research and market testing as they deem necessary to develop an evidence-based concept for the District Centre that meets the needs of existing and future communities, including engaging with the appropriate partners as required.

The property consultant will take a lead role in the following services:

- Clear identification of the project team and the specialisms to be employed to define the requirement for the District Centre evidencing the experience of your team in advising on such centres.

- Relevant property market and socio-economic data analysis as an evidence base to support advice on uses and phasing. This should be presented in a report proving an interpretation of the data and how this relates to identification of how proposed services will meet local need.

- Lead on any market testing and stakeholder engagement that is required to refine proposals around development type, phasing and delivery. This will include seeking feedback from occupiers and other relevant parties including healthcare/ education partners, as well as specialist developers with a track record in delivery of District Centres (up to a maximum of 10 parties).  Commercially sound feedback will form part of the emerging outline planning application and the consultant will ensure this is effectively shared with the wider consultant team.

- Working collaboratively and iteratively with the masterplanning consultant throughout the planning application process, to provide commercial input that supports production of indicative masterplans for the District Centre and associated residential uses which will be refined and finalised as the project progresses. Please assume 10 days of project team time for this element of work.

- Production of a phasing plan to highlight how the delivery of the District Centre will be delivered in parallel with development of the wider site, and to ensure that the health and education facilities have the necessary amenities.

- Presentation of first draft options to client team in a workshop format. These should consider the following:

  - Mix and quantum of different uses

  - Initial masterplan/ design code/ plot passports, with property consultant leading on commercial discussion

  - Phasing to ensure local centre supports wider site and meets both community need and occupier need (e.g. footfall requirements, parking, visibility, etc.)

  - Potential exit routes for Homes England.

The consultant will proactively seek feedback to refine the options in an iterative manner with the masterplanner, ultimately preparing an initial long list of options to take forward to Stage 2 viability work.

- In collaboration with the masterplanner, presentation of initial long list of options to the client team, to be supported by accompanying report summarising the process and findings of the report.

Stage 1b. Delivery Outputs:

- High-level report analysing key market and socio-economic data and identification appropriate services to meet local need.

- Commercial input into masterplans/ design codes / plot passports for the District Centre produced by masterplanner.

- Input into phasing plans for the delivery of the District Centre.

- Presentation of first draft of long list of options for the District Centre and a further presentation of final long list of options for the District Centre including potential HE exit routes.  Both presentations will include a client workshop to discuss the proposals. Workshops can be held via Teams or in person if deemed appropriate. Includes production of summary report.

Stage 1c. Masterplan Development – Custom Build/ Self Build at HE4a and HE3

There is potential for early delivery of Custom Build/Self Build plots (likely part of the ‘Dunchurch parcel’ (HE4a and HE3) there may be an option to extend the commission to manage a Custom/Self Build/SME disposal. The overall masterplan should consider options for likely demand for such opportunities, the size and location of potential plots, and likely values that could be achieved which will help guide our strategy on if, where and when we proceed with an application in this regard.

The consultant should include a fee estimate for this element of work within their fee proposal based on the assumptions set out above, and Homes England reserves the right to instruct on this at a future point if required.

Stage 1c Delivery Outputs:

- Written advice in the form of a report to help guide our strategy / current thinking.

- A workshop to discuss the report and recommendations with an option to amend the report following the workshop

Stage 2. Masterplan Testing and Refinement (including development viability)

- Review all technical documents to understand their impact on masterplan proposals and viability, and to reflect these key findings in development appraisals.

- Prepare and manage parcel level development appraisals for all Homes England landholdings, that are linked to a HE master appraisal, to test assumptions in the draft masterplan and advise on key issues that impact viability. This should include a commentary on the impact of Homes England policy objectives on overall project viability, for example, affordable housing provision, construction type (e.g. sustainability & design standards, form of construction (MMC, self-build), development type (private sale, PRS, retirement, etc.) and phasing, etc.).  This should tie in with work on Stages 1a, b and c above.  Each appraisal should sit as its own appraisal and within a comprehensive development appraisal. This should be capable of being utilised to support the outline planning application(s). Please note:

  - Development appraisals for the residential parcels will be based on the masterplan outputs of Stage 1a.

  - Development appraisals for the District Centre and associated residential parcels are required to test the long list of masterplan options produced at Stage 1b.

- Using the development appraisals, engage with Homes England’s appointed masterplanning consultants, Multi-Disciplinary/ Technical consultant, wider partners and stakeholders to test the masterplan options, and to reach the preferred option that will be progressed as the outline planning application scheme.  This will include up to four updates to each development appraisal and appropriate sensitivity testing. The final masterplan option should aim to maximise:

- The value and housing potential of the site in the context of the wider SW Rugby SUE.

- The District Centre mix and quantum of uses that meets community need.

- Scheme viability

- Achievement of Homes England policy objectives set out in Homes England Strategic Plan around MMC, SMEs, self-build, etc.

- A key element of the masterplanning instruction is to develop a masterplan to support the planning application(s) and future delivery of the site to ensure delivery of high-quality design across the individual phases. The property consultant should engage with the masterplanning consultant to provide their commercial view, and to understand what impact this could have on scheme viability.  Please assume up to 10 days project team time.

- Based on the viability work above, develop a robust and deliverable phasing strategy for the development parcels within the area identified for this appointment:

  - The phasing strategy for residential development will take account of the wider infrastructure proposals for the site and delivery timescales for other landowners so as not to create an oversupply of a particular product.

  - The phasing strategy for the District Centre and associated residential parcels will set out a preferred delivery option for the District Centre, including advice on how each option will funded. This will be informed by work in Stage 1b.

- Work with key partners including consortium members, to enable a comprehensive approach to site wide development as planning applications come forward to help to drive high quality development across Homes England landholdings. This could include advice around s106 negotiations, equalisation, etc. Please assume 10 days project team time.

- Review and provide commercial feedback into the emerging site-wide viability model that is being prepared by the consortium, to ensure that Homes England objectives are maximised. For the purpose of evaluation, please assume 15 days project team time.

- Production of summary report incorporating the above work (circa 15-20 pages excluding appendices).

Stage 2 Delivery Outputs:

- Detailed development appraisals on a phase by phase and all phase basis including District Centre.

- Detailed phasing programme for delivery of all phases of development including District Centre.

- Summary report identifying work undertaken to develop final development options, and summary of development appraisals and sensitivity testing with conclusions on final options and how this meets Homes England objectives.

- If required by the LPA, prepare a viability appraisal to support the OPA complying with the most RICS Guidance.  For the avoidance of doubt, please assume this will be required and provide an estimate of costs as part of your submission.

Stage 3. General Property Advice on Disposal Strategy for Homes England land

Just prior to the formal marketing phase of Homes England parcels/phases, Homes England requires further work to refine and confirm the disposal strategy. This includes but is not limited to the following key workstreams:

- General advice on preparation of robust disposal strategy to include:

- Market advice on values, phasing, tenure, development mix, market attractiveness, etc.  We expect consultants to identify market specialists to advise on the different development types identified in the draft phasing plan. Please note this will need to tie in with all workstreams in Stage 1a, b and c above as well as the delivery plans of other consortium members.

- Updates to development appraisals prepared at Stage 2 and valuation advice in respect of Homes England ownership to inform disposal strategy. Please assume up to 2 updates to each development appraisal.

- Advice on the Homes England exit strategy for the District Centre in the form of an options appraisal that considers long term stewardship and the management structure, underpinned by a financial appraisal of the cost implications of each option. Economic evaluation will be undertaken in house. There may be a requirement to extend this commission to include economic appraisal at a future point.

- Plot HE1b - We are in discussions with one of the consortium members for the potential disposal of part of this plot of land.  Subject to confirmation we may require the following additional services:

- Draft valuation advice to support negotiations.

- Lead role on negotiations with the developer and agreement of Heads of Terms for disposal.

- Preparation of a Red Book valuation to support agreed transaction value to demonstrate best consideration.

For the purpose of evaluation, please assume a market value of £5 million for the parcel.

- Advice on the appropriate marketing and disposal strategy for all Homes England landholdings, taking into account both the current Homestead Link Road planning application and the wider development proposals for the site, and how to achieve Homes England objectives, to ensure that we are maximising market attractiveness, engagement with SMEs, delivery of homes and value for money, clearly articulating how the strategy aligns with the Homes England Land Disposal Policy.

- Alongside preparation of the Disposal Strategy from Point 3 above, to review the Phase 1 land (Plots HE1a and HE1b only) and advise on the site-specific disposal strategy for the early disposal of this land, including advice on site parcelling, development type, interested parties/ developers, etc.  The consultant will review the DPS panel members and advise of any known contacts who should be approached with a view to joining DPS so as to maximise market exposure and SME engagement.  This work will inform the early stages of Stage 4, Site Marketing Preparation via DPS.

- To review the gap analysis of existing data & warrantable reports that will be prepared by the technical consultant, and to advise on any additional work required to support the marketing of the site, with a view to reducing the risk of project timescale slippage and post tender price adjustments.

- On-going market advice as the emerging outline planning application is progressed, building on work undertaken in stages 1 & 2. Please assume 3 days of project team time.

- Commercial advice on general development issues and opportunities as they may arise. For ease of evaluation your response should include your approach and fee for the following activities:

  - Advice on potential land transactions with wider site landowners, including residential and commercial. For the purposes of evaluation, please assume 10 days project time in pricing.

  - Negotiated disposals and/or acquisition – For the purposes of evaluation, please assume a requirement for support in negotiating three negotiated disposals each with a market value of £5 million.

  - Provision of a franking valuation to support activities a and b above for an asset with a market value of £5 million (please assume a requirement for three franking valuations)

  - Provision of a red book valuation to support activities a and b above for an asset with a market value of £5 million (please assume a requirement for three red book valuations).

  - Advice on on-going discussions with consortium members.  For the purposes of evaluation, please include an assumption for 1 day a month of project team time for the 3-year contract term. Please note if a particular issue arises that requires significantly more input than anticipated, we will provide the opportunity to submit a revised fee proposal.

  - Advice on valuation implications of key decisions to be taken in respect of s106 negotiations/ land roof tax / infrastructure delivery. For the purposes of evaluation, please assume 5 days project time in pricing.

Stage 3 Delivery Outputs:

- Disposal Strategy for all Homes England landholdings that aligns with Homes England Land Disposal Policy.

- Advice on Homes England exit strategy for District Centre.

- Initial advice on disposal strategy for Phase 1 land.

- Input into gap analysis of existing data & warrantable reports.

- Commercial advice on development issues

The following stages 4 – 7 are for Phase 1 disposals only (HE1a and HE1b), although a fee quote is requested for plots HE3 and HE4a:

Stage 4. Site Marketing Preparation via DPS

The purpose of this stage is to confirm the disposal strategy for the Phase 1 land, and to secure board approval to proceed to Stage 5, Site Marketing and Disposal.

We will be disposing of the site using the newly procured Homes England Dynamic Purchasing System via a ‘Call for Competition’. This comprises a Stage 1 ‘Expression of Interest’, followed by Stage 2 ‘Tender Stage’.  Please note that the Stage 1 Expression of Interest is to be completed prior to seeking board approval within this workstream, see point 6 below.

- Initial advice on preparing the marketing strategy for the site via DPS including articulation of market testing strategy, approach to drafting marketing documents, Call for Competition, etc.

- Soft Market Testing with all relevant DPS Members to get their views on the site to gain perspectives to inform the Call for Competition Tender Stage documentation including pace, MMC requirements and deferred payment. This will include a market testing questionnaire (based on a Homes England template) to test opinions around key issues including market interest, parcel size, sales revenues, sales rates, phasing, build costs, MMC, custom build, design aspirations, affordable housing mix and grant funding, etc. and the consultant will produce summary report highlighting key points that influence the disposal strategy.

- In conjunction with the technical consultant, to advise on the extent and scope of the Tender Pack required to support marketing of the site. For information, please note DPS Technical Pack Checklist at Appendix A.

- Based on work undertaken at Stage 3 (item 3), finalise the marketing and disposal strategy for the phases referred to above, taking into account both the planning status and the wider development proposals for the site.

- Agree upfront a robust programme for the development partner selection process including the key stages and outputs.

- Management of Call for Competition Stage 1 (Expression of Interest) via ProContract including preparation of documentation required for ProContract (site information, redline plan, illustrative masterplan and indicative disposal timeline) to enable developers to determine and confirm whether the opportunity is right for them. This will be required for each disposal.

- Contribute to a Gateway 3 (G3) report to secure formal Homes England approval to the marketing and disposal strategy for the above phases.  The G3 paper will include a summary of market testing process and outcomes from Expression of Interest, as well as confirmation of disposals parameters (policy objectives around MMC, pace, design), evaluation criteria and weightings and deferred payment parameters.  A single G3 approval is required that sets out the disposal strategy for all Homes England landholdings.

Stage 4 Delivery Outputs:

- Market testing report

- Input into Tender Pack

- Marketing and disposal strategy for Phase 1 land

- Procurement programme for selection process

- Completion of Call for Competition Stage 1 Expression of Interest

- Input into G3

Stage 5.  Site Marketing and Disposal via DPS

The appointed property consultant will be required to manage the site marketing process for each parcel of land within Phases HE1a and HE1b as per the assumptions set out above, including administering all requirements of the DPS process.  A fee proposal is also required for HE3 and HE4a.

Site marketing and disposal via DPS will include, but is not limited to, the following key responsibilities for each disposal process.  (Please note further information individual disposal processes at Table 1 below)

- Preparation of the Tender Pack to include all marketing documents, technical information and Tender Forms required for DPS Call for Competition Stage 2 for issue to bidders via ProContract

- Management of Call for Competition Stage 2a ‘Initial Questions’ and Stage 2b ‘Invitation to Tender’ via ProContract, including uploading all required documents, all communication with interested parties, managing the DPS and clarification process, preparation of documentation required for ProContract and support in shortlisting bidders.  Please assume a 2-stage process will be required comprising Stage 2a ‘Initial Questions’ and Stage 2b ‘Invitation to Tender’.

- Develop the scoring criteria in collaboration with Homes England and support/ advise in the evaluation and assessment of Stage 2a Initial Questions and Stage 2b ITT returns.

- Ensure robust sign off processes for assessment, moderation and client approvals for audit purposes.  Please note, the appointed agent is expected to take a lead at the Developer clarification sessions (There will be 2 of these sessions per developer at ITT stage) and ITT moderation meetings.

- Preparation of a “Marketing and Tender Evaluation Report” detailing the marketing and evaluation process, assessments of all developer appraisals leading to a clear recommendation for the preferred development partner and, where appropriate, under bidder.

- Provide a “Franking Valuation Report” Please note value assumptions set out below to support pricing.

- Input into the drafting for the Gateway 4 (G4) report to secure formal Homes England approval to the selection of the preferred development partners.

Please note following value assumptions in Table 1 below to be assumed in pricing:

Table 1 – Value assumptions for each disposal

| Disposal | Parcel name | Sub parcel | Units | Timescales | Assumed value £m |
| --- | --- | --- | --- | --- | --- |
| Phase 1 |  |  |  |  |  |
| Disposal 1 | HE1a | SME | 73 | 2025/26 - 2026/27 | 3.3 |
| Disposal 2 | HE1a | PRS | 190 | 2025/26 - 2026/27 | 8.7 |
| Disposal 3 | HE1b | Negotiated | 70 | 2025/26 - 2026/27 | 3.2 |
| Disposal 4 | HE1b | HE land | 100 | 2026/27 - 2028/29 | 4.6 |
| Disposal 5 | HE1d | Commercial | N/A | N/A | N/A |
| Disposal 6 | HE1d | Residential | 100 | 2025/26 - 2027/28 | 4.6 |
| Disposal 7 | HE1e | O&H | 53 | 2025/26 - 2026/27 | 2.4 |
| Disposal 8 | HE2 | Standard | 73 | 29/30-30/31 | 3.3 |
| Disposal 9 | HE2 | Retirement | 140 | 26/27-28/29 | 6.4 |
| Phase 2 |  |  |  |  |  |
| Disposal 10 | HE3 | MMC | 127 | 2026-27 and 2028-29 | 5.8 |
| Disposal 11 | HE4a (1) | Residential | 124 | 2030/31 - 34/35 | 5.7 |
| Disposal 12 | HE4a (2) | Residential | 124 | 2030/31 - 34/35 | 5.7 |

Stage 5 Delivery Outputs:

The following outputs are required for each disposal of a development parcel via DPS:

- Final marketing documents

- Management of ProContract including uploading all documents

- Scoring criteria and evaluation documents

- Marketing and Tender Evaluation Report

- Franking Valuation Report

- Input into G4 report

Stage 6. Legal negotiations to Contract Award for each disposal process

- Support to legal advisor in preparation of Heads of Terms and provide negotiation support in concluding an “Agreement for Lease” with the selected development partners, including advice on any post tender price adjustments.

- Liaison with Homes England disposals team.

- Liaison with Homes England’s legal and technical consultants as necessary in concluding the “Agreement for Lease” and “Building Lease” with the selected development partner.

- Liaise and work in partnership with the appointed solicitors.

- Liaise and discussion with local planning authority and other bodies as appropriate.

Stage 6 Delivery outputs:

- Support to legal advisor as required

Stage 7. Post contract monitoring

There may be a requirement for advice post contract award. This could include providing a response to post contract award changes, and may also require additional valuation advice. For the purpose of evaluation, in your methodology please refer to your view on what support may be required, and please price for the following:

- One ‘major’ deed of variation that necessitates an updated (site specific) development appraisal plus an assumed 3 of days project team time.

- Two ‘minor’ deeds of variation, such as a land swap, that requires an assumed 5 days of project team time in total.

Stage 7 Delivery outputs

- Development appraisals

- Input into deeds of variation

# Indicative Programme

- Suppliers should note the indicative programme dates when preparing their Programme information in the Response Form. Suppliers are asked to identify any key risks to delivery of this programme in their response.

| Milestone | Indicative |
| --- | --- |
| Site acquired | June 2020 |
| HLR Full Application Submitted | Summer 2022 |
| HLR Full Application Determined | Winter 2022 |
| Commencement of procurement of HLR Contract | Winter 2022 |
| HLR Technical Approvals | Spring 2023 |
| Hybrid planning application submitted - Cawston Lane/ Community Spine (Full) Homes England ‘Red’ land (outline) | Spring 2023 |
| HLR Works | Summer 2023 – Summer 2024 |
| Hybrid planning application determined - Cawston Lane/ Community Spine (Full) Homes England ‘Red’ land (outline) | Autumn 2023 |
| Procurement of Cawston Lane/ Community Spine works | Autumn 2023 – Spring 2024 |
| Cawston Lane/ Community Spine works | Summer 2024 – Autumn 2024 |
| First G3 – Homes England Board Approval of Disposal Strategy | Summer 2023 |
| First disposal of Homes England land parcel | Summer 2023 – Summer 2024 |
| Conditional contract for first disposal | Summer 2024 |
| Reserved matters for first disposal | Spring 2025 – Summer 2025 |
| Unconditional contract for first disposal | Spring 2025 |
| Construction commences for first disposal | Summer 2025 |
| Development end date for Homes England final phase | Summer 2037 |

# Management

# Homes England Personnel

- The Supplier will be managed on a day-to-day basis by a named Senior Development Manager who will be identified as the primary point of contact at Homes England. The wider project team includes (please note names will be confirmed after contract award):

- Project Director – project oversight.

- Head of Planning & Enabling – responsible for overall project delivery for this commission for Stage 1 & 2

- Head of Disposals – responsible for overall project delivery for this commission for Stage 3 onwards

- Project Manager/ Senior Planning & Enabling Manager for Stage 1 & 2.

- Senior Development Manager (who will take role of project manager from Stage 3 onwards)

# Other Personnel

- The Supplier needs to work with the wider consultant team as set out in Section 1.4 above.

- Other key Partners that the Supplier will need to work with include Rugby Borough Council, Warwickshire County Council, and the Consortium Members (Taylor Wimpey and Richborough Estates in particular).

# Meeting Requirements

- Please note, attendance at the following meetings should be priced within your fee for each Stage of work of The Services as set out at Section 2 above.

Start-up meeting

- We require two start up meetings, one to be held with Homes England only, and a second ‘consultant’ start up meeting to introduce the wider consultant team and agree project management / governance requirements.  You are required to confirm attendance at these meetings as part of your response.  Please assume each meeting will last for 2.5 hours and will require attendance from your project lead and project manager as a minimum.

Project meetings

- The requirement for these meetings will change throughout the course of the project and intensify at key milestones.  You are required to confirm attendance at these meetings as part of your response.  For the purpose of evaluation, please assume a fortnightly meeting is required for the duration of the 3-year contract.   Please assume each meeting will last for 2.5 hours and will require attendance from your project lead and project manager as a minimum.

Contract review meetings

- For the purpose of evaluation, please assume a requirement for quarterly contract review meetings. You are required to confirm attendance at these meetings as part of your response.  Please assume each meeting will last for 2.5 hours and will require attendance from your project lead and project manager as a minimum.

Poor Performance Meeting

- These meetings will hopefully not be required.  However, if poor performance is repeated following escalation to the Supplier’s Key Personnel to resolve the issue, as required in the Framework Management Schedule of the Framework Contract, the Framework Manager must be notified and Homes England may call for a Poor Performance Meeting.  Beforehand, Homes England will present areas of concern so that the Supplier and Homes England can discuss what happened and why, what will be done to prevent it happening again and how matters will improve.  The Supplier subject to such a meeting would be expected to outline in writing in a Rectification Plan afterwards what improvements/modifications they will be putting in place.  There will be a maximum of two Poor Performance Meetings before termination of the commission.

# Invoicing

- This will be agreed at project inception and will include a mix of regular time-based invoicing and fixed fees for key delivery outputs. The successful consultant will keep Homes England informed of spend against budget using the submitted fee schedule format to maintain a clear audit trail.  In the event of key changes in consultant personnel, the consultant will submit an up-to-date fee schedule and attend a meeting to discuss prior to departure of that individual.

# Other Requirements

# Termination

- Should performance during the period of this appointment prove unsatisfactory following the Poor Performance meeting provisions set out in the Management section above, Homes England will exercise its right under the Termination and Suspension of the Contract clause in the Framework Contract to give notice to terminate the arrangement with immediate effect.

- If the services are no longer required, for whatever reason, then Homes England reserves the right to terminate the appointment and pay for services completed at that point.

# Conflict of Interest

- Homes England will exclude the Supplier if there is a conflict of interest which cannot be effectively remedied. The concept of a conflict of interest includes any situation where relevant staff members have, directly or indirectly, a financial, economic or other personal interest which might be perceived to compromise their impartiality and independence in the context of the procurement procedure.

- Where there is any indication that a conflict of interest exists or may arise then it is the responsibility of the Supplier to inform Homes England, detailing the conflict in a separate Appendix.

# Confidentiality

- This Further Competition ITT and associated information is confidential and shall not be disclosed to any third party without the prior written consent of Homes England.  Copyright in this Further Competition ITT is vested in Homes England and may not be reproduced, copied or stored on any medium without Homes England's prior written consent.

- Suppliers shall not undertake, cause or permit to be undertaken at any time any publicity in respect of this Further Competition process in any media without the prior written consent of Homes England.

# Future changes to scope of works

- Note that it is recognised that as the commission progresses and the disposal strategy evolves, the scope of works may change and as such Homes England retain the ability to discuss any amendments beyond what has been priced for in this tender with the appointed consultant at the appropriate time. Provision has therefore been made to amend / extend the scope of the commission either through supplementing existing or adding new work stages.

- Bidding consultants are NOT asked to price for any changes at this stage.  If these services are required this will be discussed with the appointed consultant.

- Although any changes are anticipated to remain with this existing scope (i.e. one phase delayed), if any additional work is required, it will be subject to further agreement/approval by the Agency in writing and via TMS and will be based on value for money assessments. Additional work will be commissioned at hourly/daily rates directly related to the scope of works required and agreed.

- Please note, additional scope of works will be up to a maximum of 50% of the original instruction, in order to remain compliant with Agency Procurement requirements.

# Framework Contract

- Any proposed changes to the existing Framework Contract should be raised as a clarification so that these can be clarified prior to ITT submission e.g. professional liability, indemnities, insurances, etc.

# Part 2 - Instructions for Submitting a Response

# General

- The Further Competition deadline is on 28/09/22 at 12PM and tender responses must be submitted on ProContract.  Please regularly check ProContract for any amendments to the Further Competition deadline. For all ProContract portal issues please contact ProContractSuppliers@proactis.com.

- Suppliers must ensure that suitable provision is made to ensure that the submission is made on time.  Any tender responses received after the Further Competition deadline shall not be opened or considered unless Homes England, exercising its absolute discretion, considers it reasonable to do so.  Homes England, may, however, at its own absolute discretion extend the Further Competition deadline and shall notify all Suppliers of any change via ProContract.

- Please note all communications during the tender period will be via the ProContract website. All Suppliers that have registered their interest for the Procurement will receive a direct email notification from ProContract on any updates via the Suppliers registered email address.  No approach of any kind should be made to any other person within, or associated with, Homes England.  It is the Suppliers responsibility to check the ProContract website for any updates to the Procurement process.  No claim on the grounds of lack of knowledge of the above mentioned item will be entertained.

- The Supplier should check the Further Competition ITT for obvious errors and missing information.  Should any such errors or omissions be discovered the Supplier must send a message via the messaging function on ProContract.  No alteration may be made to any of the documents attached thereto without the written authorisation of Homes England.  If any alterations are made, or if these instructions are not fully complied with, the tender response may be rejected.

- All clarification requests must be sent using ProContract no later than 5 working days before the Further Competition deadline shown on ProContract.  Any queries submitted after this may not be answered.  Homes England will respond to clarifications as soon as practicable.

- Suppliers should specify in their clarification questions if they wish the clarification to be considered as confidential between themselves and Homes England. Homes England will consider any such request and will either respond on a confidential basis or give the Supplier the right to withdraw the clarification question.  If the Supplier does not elect to withdraw the question and Homes England considers any clarification question to be of material significance, both the question and the answer will be communicated, in a suitably anonymous form, to all prospective Suppliers who have responded.  If Suppliers consider that page limits set out in Section 20 (Evaluation Criteria) are insufficient to provide the information required by the question then a clarification request should be raised.  No guarantee can be given that the page limit will be increased.

- Tender responses must not be accompanied by statements that could be construed as rendering the tender response equivocal and/or placing it on a different footing from other Suppliers.  Only tender responses submitted without qualification strictly in accordance with the Further Competition ITT (or subsequently amended by Homes England) will be accepted for consideration.  Homes England’s decision on whether or not a tender response is acceptable will be final.

- Tender responses must be written in English.

- Under no circumstances shall Homes England incur any liability in respect of this Further Competition or any supporting documentation.  Homes England will not reimburse the costs incurred by Suppliers in connection with the preparation and submission of their tender response to this Further Competition.

- Homes England reserves the right to cancel this Further Competition process at any time.

# Quality

- A Response Form template has been provided in Part 2 to respond to the Quality questions detailed in Section 20 (Evaluation Criteria).  The Response Form must be completed and returned as part of the tender response.

- Suppliers must provide information on proposed staff in the Response Form and Resource and Pricing Schedule provided in Part 2.  If the Supplier is a consortium or intends to sub-contract the Services, in whole or in part, then it should specify precisely in the Resource and Pricing Schedule which economic operator shall perform the Services (or parts thereof).

- PLEASE NOTE: The Resource and Pricing Schedule will be scored qualitatively as part of the overall quality response. The schedule lists out the services that are required for the financial bid, the appropriateness of the quantum and seniority of resource will be scored as part of the quality bid.  For example, if a particular workstream does not have an appropriate time resource or seniority allocated, it can be scored down.

# Pricing

- A Resource and Pricing schedule has been provided with this Further Competition ITT which must be completed and returned as part of the tender response.  Please note comments above that state that allocation of resource will be part of the quality evaluation.

- The pricing approach for this Further Competition is a lump sum fixed fee for Stages 1 and 2 (Masterplan Development and Masterplan Testing and Refinement), and an indicative fixed fee for Stages 3 – 6.

- It is acknowledged that some elements of the work within Stages 3 – 6 will be subject to change and/or confirmation as the Disposal Strategy for the site develops, for example site parcelling and phasing has been confirmed, any potential acquisition or disposal requirements are known.

- For the purpose of evaluation and budgeting, the indicative fee for Stages 3 – 6 should be robust and based on the assumptions provided in this ITT.  As the precise requirement is understood, there will be opportunity to resubmit your fee proposal for this element of the work. Please note, this will be subject to approval from Homes England and must be based on the original assumptions set out in your fee proposal.

- By way of example:

  - Stage 3, Step 7 – there is a requirement for commercial advice on development issues as they may arise. This could include a negotiated disposal. Your original fee proposal should clearly show your resourcing assumptions for a site with a market value of £5 million. If a negotiated disposal is required, and the value of the site better understood, you will be required to submit a revised fee proposal for the disposal that clearly matches the resourcing assumptions in your original submission.

  - Stage 4, Step 6 - there is a requirement for an EOI process for each parcel to be disposed of through DPS. Once site parcelling and phasing is confirmed, the fee approval for this element of the work can be fixed as we will have certainty on the number of parcels. Your revised fee will clearly show that the price per disposal matches that submitted in your original submission.

- The table below illustrates those stages of work that we anticipate may require an opportunity to resubmit the fee proposal:

| Stage | Pricing | Commentary |
| --- | --- | --- |
| Stages 1 & 2 - Masterplan Development and Masterplan Testing and Refinement | Fixed price | Stages 1 & 2 will be a fixed price |
| Stage 3 - General Property Advice on Disposal Strategy | Fixed price | Step 1 – general advice on disposal strategy Step 3 – Disposal strategy for HE land Step 4 – Review site specific disposal strategy for Phase 1 land Step 5 – gap analysis |
|  | To be refined when requirement known | Step 2 – potential disposal of part of HE1b Step 6 – Advice to emerging OPA, assume 3 days but will be confirmed Step 7 – Indicative budget to be confirmed when requirements known |
| Stage 4 Site Marketing Preparation Via DPS | Fixed price | Steps 1 – 5 Site Marketing Preparation Step 7 G3 report |
|  | To be refined when requirement known | Step 6 – Call for Competition Stage, EOI – when number of disposals known fee for this element can be revised if required. |
| Stage 5 Site marketing and Disposal via DPS | To be refined when requirement known | Indicative fee to be submitted for all steps based on value assumptions set out in Table 1. This will be revised as site specifics understood. |
| Stage 6 Legal negotiations | Fixed fee | Fixed fee to be submitted based on your commercial judgement of the resourcing requirements for this stage of work. Opportunity to refine only if this stage becomes protracted and subject to approval. |
| Stage 7 Post contract monitoring | To be refined when requirement known | Indicative fee to be submitted based on assumptions provided |

- An allowance should be included for expenses as part of the overall fee proposal, please note these will not be chargeable separately unless agreed in advance by Homes England and in exceptional circumstances where there is demonstrable need for the increased expense. It is anticipated that fees will be paid monthly in arrears, up to the satisfactory completion of specific milestones/ tasks/ packages of work.

- The list of activities in the Resource and Pricing Schedule is not exhaustive and there may be additional duties/services required that will emerge as work is undertaken.  This commission may be extended on client instruction to cover such matters as arise, based on a time charged fee schedule completed in the tender response.  The commission will only be extended if the services relate to the original objective of the overall call off contract.

- Suppliers are reminded that day rates for all individuals must be the agreed Framework Contract rates unless discounted rates are offered and will be used for all of the services.

# Evaluation

- Tender responses will be evaluated on the basis of the overall most economically advantageous Tender (MEAT) submitted to Homes England.  The evaluation criteria (and relative weightings) that Homes England will use to determine the most economically advantageous Tender are set out in Section 7 (Evaluation Criteria) below and the scoring approach is detailed in Section 8 (Worked Example).  Scores will be rounded to two decimal places.

- Evaluators will initially work independently. Once they have completed their independent evaluation they will meet to discuss, understand and moderate any differences they have via a consensus meeting, where a single consensus score for each question will be agreed.

- Award decisions will be subject to the standstill period if over the EU Services threshold.  Unsuccessful Framework Suppliers will be provided with their scores and feedback to explain the award decision.

# Documents to be Returned

- Suppliers are expected to provide the following information in response to this Further Competition ITT:

- Completed Response Form

- Completed Resource and Pricing Schedule

# Procurement Timetable

- The procurement timetable that Homes England is working towards is set out below. Please note that this is indicative only, any changes will be communicated via ProContract.

| Stage | Milestone | Date |
| --- | --- | --- |
| Stage 3 - ITT | Issue Invitation to Tender | Tuesday 23 August |
|  | Clarifications deadline for bidders | Wednesday 21 September |
|  | Clarification response deadline | Monday 26 September 4PM |
|  | ITT Submission Deadline | Wednesday 28 September 12PM Monday 5th October 11AM |
|  | ITT Evaluation Period | Wednesday 12 October |
|  | Alcatel period (10 calendar days) and Cabinet Spend Approval (10 business days) | Wednesday 26 October |
|  | Notification of successful bidder | Thursday 27 October |
|  | Contract commencement | Monday 7 November |

- ProContract will provide the most up to date information regarding timescales.

# Evaluation Criteria

| Quality will account for 70% of the Overall Score. The following scoring methodology will apply: 5 – Excellent Satisfies the requirement and demonstrates exceptional understanding and evidence in their ability/proposed methodology to deliver a solution for the required supplies/services. Response identifies factors that will offer potential added value, with evidence to support the response. 4 – Good Satisfies the requirement with minor additional benefits. Above average demonstration by the Supplier of the understanding and evidence in their ability/proposed methodology to deliver a solution for the required supplies/services. Response identifies factors that will offer potential added value, with evidence to support the response. 3 – Acceptable Satisfies the requirement. Demonstration by the Supplier of the understanding and evidence in their ability/proposed methodology to deliver a solution for the required supplies/services. 2 - Minor Reservations Some minor reservations of the Supplier’s understanding and proposed methodology, with limited evidence to support the response. 1 – Major Reservations/Non-compliant Major reservations of the Supplier’s understanding and proposed methodology, with little or no evidence to support the response. 0 - Unacceptable/Non-compliant Does not meet the requirement. Does not comply and/or insufficient information provided to demonstrate that the Supplier has the understanding or suitable methodology, with little or no evidence to support the response. PLEASE NOTE: If your response scores 0 or 1 for any one question your overall submission will be deemed as a fail. Any text beyond the specified page limits below will be ignored and will not be evaluated. Homes England will not cross-reference to other answers when assessing quality responses, unless otherwise specified. Evaluators will initially work independently. Once they have completed their independent evaluation they will meet to discuss, understand and moderate any differences they have via a consensus meeting, where a single consensus score for each question will be agreed. |  |  |  |
| --- | --- | --- | --- |
| Number | Criteria | Demonstrated by | Weighting |
| 1 | Technical Merit of Proposal PAGE LIMIT: Maximum 6 A4 pages, 11-point Corbel font | - A Methodology Statement that outlines the approach for each of the required services, outlining the key deliverables for each stage. Explain how the commission will be undertaken, and by who to link their experience that is relevant to the project. Outline where other supplier input may be required. - For each of the services required, provide a clear indication of the team’s capacity to undertake, innovate, add value and demonstrate value for money. - Explain how you will support the wider consultant team, and notably the masterplanning appointment, in ensuring that high-quality design, landscaping, stakeholder engagement and commercially aware placemaking will be aligned to infrastructure delivery requirements. - Describe how the team will approach the phasing and disposals strategy to maximise the site’s viability, attractiveness and deliverability to the market, setting it apart from its competitors nearby. - Explain how you will balance your advice to Homes England as master developer, with our role as landowner to ensure that we maximise best value in disposal of our own land interests, whilst maximising the wider SUE potential. - Please provide a summary of your relevant experience to demonstrate your track record in delivering advice in respect of similar services required under this brief for projects of a similar scale and complexity. Relevant local/ regional examples or comparable projects in terms of similar market specifics is essential. This should highlight your experience of maximising housing delivery with an emphasis on placemaking. Please include specific evidence of delivery of local centres and how this was tied in with wider scheme delivery to promote community and sustainability. Please highlight key personnel and their role in the project to illustrate how this experience links with the resources identified in Q3. - Please highlight any other information that may be required to support delivery of your methodology, or to address any gaps in information, for instance additional surveys or appointments. | 30% |
| 2 | Understanding of Project Requirements PAGE LIMIT: Maximum 3 A4 pages, 11-point Corbel font (excluding risk register) | - Please set out your understanding of the strategic context of the site, and how your methodology set out in Q1 above will support Homes England objectives both as master developer and as landowner. - Please provide a draft risk register that details key risks and issues, and where appropriate identify the potential impact of external influences and stakeholders, and what actions you will take to ensure that these are mitigated and/or addressed, to support achievement of our strategic objectives. - Outline your approach to balancing the requirements of a significant infrastructure led development across multiple stakeholders, with a key requirement to support project viability at the land parcel level, with Homes England requirements around high quality design and placemaking. Please identify your understanding of value engineering and how this could be successfully applied to the scheme. | 10% |
| 3 | Staff and other Resources PAGE LIMIT: Maximum 5 A4 pages, 11-point Corbel font (excluding CVs and structure chart) | - Describe who will undertake the commission and key accountabilities with a team structure chart. - Explain how work packages will be coordinated between the project team to ensure effective decision taking and information sharing with multiple project consultants. - Demonstrate the lead team members’ recent relevant experience from similar projects, highlighting team members’ with specific experience of delivery of district centres. - Give evidence of collaborative working with stakeholders and third-party delivery partners to add value, ensure quality, mitigate risk and respond to lessons learned. - Provide a Resource and Pricing Schedule (not included in the 5-side limit). Please see attached separate Excel file to be completed. - Provide CVs for key members of staff (CV’s not included in the 5-side page limit, maximum 2 pages per CV). - State where any other supplier input will be required and how this would be managed. | 15% |
| 4 | Management and Communication PAGE LIMIT: Maximum 4 A4 pages, 11-point Corbel font | - Summarise the approach you propose for project management to coordinate multiple workstreams, including identification of key personnel with responsibility for managing the overall quality of service, as well as managing the team and reporting to the client. - Explain how the team will meet the project objectives to deliver at pace, achieve high quality design, include the community and ensure value for money. - Outline the key project tools that you propose to use to effectively manage information, resources and actions within the project team and with external stakeholders. - Explain how the client relationship and decision-making will be managed, with reference to options analyses and change control processes. - Please clearly identify the number and regularity of client meetings / site visits, and who will attend, and what will be discussed at each meeting/ what the purpose of each meeting will be. Please note meeting assumptions set out in Part 1, Section 5.2, Meeting Requirements. - Support your answer with relevant examples where your team has added value to past projects that involved phased infrastructure delivery. Cross referencing with previous responses is permitted. - Please confirm that you do not have a conflict of interest associated with this commission. If there is a perceived conflict, please identify this so that this can be reviewed as part of tender clarification. | 10% |
| 5 | Programme PAGE LIMIT: Maximum 3 A4 pages, 11-point Corbel font (excluding programme/ chart) | - Provide a programme for appropriate work packages and deliverables that responds to the milestones and key trigger points in the project. Please confirm any viewpoints on whether the milestones provided are achievable. Please provide an indicative project programme in excel format that demonstrates these milestones. - Identify risks which may affect the programme or costs, what impact they may have, and any mitigation. - Describe how the team would coordinate different workstreams to track progress, mitigate the risks/ costs, inform the phased delivery and identify opportunities to add value. To enable like for like comparison we have set out 7 stages of work in this ITT brief. Please comment on these. Identify any other information or items that you feel should fall within the scope to fulfil the brief. Make clear any additions, deletion, variations, exclusions or limitations. | 5% |

| Price will account for 30% of the Overall Score. The lowest price will gain the maximum marks with other prices expressed as a proportion of the best score using the maths explained in the worked example below. |  |  |
| --- | --- | --- |
| Criteria | Demonstrated by | Weighting |
| Price | Completed Resource and Pricing Schedule | 30% |

# Worked Example

How your quality scoring will be used to give a weighted score:

| Bidder | Question | Score out of 5 | Weighting | Weighting Multiplier | Weighted Score | Total Weighted Score |
| --- | --- | --- | --- | --- | --- | --- |
| Supplier A | 1 | 2 | 30% | 6 | 12 | 33 |
|  | 2 | 3 | 10% | 2 | 6 |  |
|  | 3 | 3 | 15% | 3 | 9 |  |
|  | 4 | 2 | 10% | 2 | 4 |  |
|  | 5 | 2 | 5% | 1 | 2 |  |
| Supplier B | 1 | 5 | 30% | 6 | 30 | 59 |
|  | 2 | 4 | 10% | 2 | 8 |  |
|  | 3 | 4 | 15% | 3 | 12 |  |
|  | 4 | 3 | 10% | 2 | 6 |  |
|  | 5 | 3 | 5% | 1 | 3 |  |
| Supplier C | 1 | 2 | 30% | 6 | 12 | n/a (fail)* |
|  | 2 | 1 | 10% | 2 | n/a |  |
|  | 3 | 2 | 15% | 3 | 6 |  |
|  | 4 | 2 | 10% | 2 | 4 |  |
|  | 5 | 2 | 5% | 1 | 2 |  |

* in the example above Supplier C’s pricing will not be scored

Worked example of how your price will be used to calculate a score

| Bidder | Form of Tender price | Lowest price/Supplier’s price (as %) | Price Score (out of 30) |
| --- | --- | --- | --- |
| Supplier A | 350 | 350/350 = 100% | 100%*30 = 30 |
| Supplier B | 700 | 350/700 = 50% | 50%*30 = 15 |
| Supplier C | 250 | n/a | n/a |

Worked example of Overall Score and Ranking

| Bidder | Total Quality Score | Price Score | Total Score | Ranked Position |
| --- | --- | --- | --- | --- |
| Supplier A | 33 | 30 | 63 | 2 |
| Supplier B | 59 | 15 | 74 | 1 |
| Supplier C | n/a | n/a | n/a | n/a |

# Part 3 Response Form

- Response Form

| Framework: | [insert] |
| --- | --- |
| Project Title: | [insert] |
| ProContract Identification Number: | DN [insert] |
| Supplier: | [insert] |
| Date: | [insert] |

To enable Homes England to evaluate your tender, we require Suppliers to respond to the questions in the format below whilst making reference to the evaluation section above.  Suppliers may use their own document but it must follow the format below.

Please refer to the evaluation section for page limits for each question.  Any text beyond this will be ignored and will not be evaluated.

1. Technical Merit of Proposal

2. Understanding of Project Requirements

3. Staff and other Resources

4. Management and Communication 5. Programme

- Resource and pricing schedule

Supplier to submit a completed Resource & Pricing Schedule in excel format to facilitate evaluation.

# Appendix A DPS Technical Pack Checklist

Delivery Partner DPS Technical Pack Checklist

| Topic | Type | Commentary |  |  | Have? | Getting? | By Whom | When? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Reports | Ecology | - Birds, Bats, Badgers, Newts, Flora & Fauna - Biodiversity Agenda - Nutrient Neutrality [where applicable] |  |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  | Site Investigation | - Desktop, intrusive investigation and remediation strategy - Invasive weeds |  |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  | FRA | - Storm & foul strategies [see nutrient neutrality above] |  |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  | Archaeology | - Below ground and historic structures |  |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  | Noise | - Could be combined, could be one or the other - Site emitting or external sources |  |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  | Vibration |  |  |  |  |  |  |  |
|  | Air Quality | - Contaminants - Malodourous |  |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  | Arboriculture | - Survey, tree protection and TPO’s |  |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  | Asbestos Register or Pre-demo Survey | - Occupied buildings should have a Register - Disused to be surveyed |  |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  | Rights of Light | - Check title for positive covenants and neighbouring titles for restrictive covenants |  |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  | Wind Microclimate | - If applicable for high-rise development only |  |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  | UXO | - MOD sites - City centres |  |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  | Landscape Strategy | - Biodiversity Net Gain |  |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  | Party Wall Matters | - Buildings on boundary - Walls |  |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  | TIA | - Existing traffic generation, permitted uses - Predicted generation |  |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  | Energy Strategy | Renewables | - PV - Solar |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  |  | Heating | - No gas from 2025 - Heat Pumps |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  |  | Electric Vehicles | - Charging provision |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  | Sustainability Strategy | - Carbon reduction |  |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
| Surveys | Topographic | - Full survey including, drainage, building floor levels, boundaries, surrounding roads and neighbouring detail - Elevations of surrounding structures |  |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  | Measured Building Survey | - Listed / retained buildings |  |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  | Building Structural Condition Survey | - Retained / refurbished buildings |  |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  | River wall condition Survey | - To show type of structure and condition - if possible with schedule of remediation works. |  |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  | Drainage Survey [CCTV] | - Minimum requirement is for outfall pipe |  |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  | Below Ground Services | - Electronic trace for all cables, conduits, pipelines and/or Slit trenching |  |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  | Below Ground Structures | - Radar, geomagnetic and other non-intrusive techniques and/or Slit trenching/ trial pitting |  |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  | Historic Maps | - Should be part of SI |  |  | [P/X] | [P/X] |  | [Insert date] |
| Records | Public sewers | - Water Authority records |  |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  | Highways | - Local authority adoption plan |  |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  | Environment Agency | - Flood plain - Landfill Sites - Groundwater Protection Zones |  |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  | Statutory Undertakers | Gas | - National Grid |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  |  | Water | - Local Water Company |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  |  | Electric | - Local Electric Company |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  |  | BT | - Openreach |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  |  | CATV | - Various |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  |  | Mobile Telecoms | - Various |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  |  | Fibre Networks | - Various |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [insert date] |
|  | Mining Records | - Go to http://mapapps2.bgs.ac.uk/coalauthority/home.html |  |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  | Rail/Tram Lines | - Network Rail - London Tube/Regional Metro lines |  |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  | Existing building Services | - Utility providers info to facilitate demo |  |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
| General Data | Title Plan | - inc. report & charges register |  |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  | Contract Plan | - Defining site under consideration |  |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  | Planning Notices | - Decision notices |  | - Outline/RM/Appeal consents | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  |  | - Conservation Area - Listings |  | - Structures/AONB/ SSS | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |
|  | Existing Building Floor Plans | - inc. ft2 for CIL calculation |  |  | [P/X] | [P/X] | [Insert tbc/name/title/refs] | [Insert date] |

Rev D. Jan 2021

enquiries@homesengland.gov.uk

0300 1234 500

gov.uk/homes-england